## Sheet1
Ref | Potential Future Change / Issue | Type | Why It Has Been Identified | Possible Trigger / Scenario | Current Position
FC-001 | Centralised Identity & Access Management | Enhancement / Architecture | v1 local Linux IAM creates duplicated account lifecycle administration across hosts. | Increasing server/user count, account drift, orphaned accounts, excessive joiner/leaver administration. | Deferred from v1
FC-002 | IAM Configuration Automation | Enhancement | Local accounts/groups could eventually be maintained consistently through automation. | Repeated manual account changes become time-consuming or inconsistent. | Planned progression after manual administration
FC-003 | Introduce Ansible | Automation / Enhancement | Configuration management could improve repeatability across multiple Linux hosts. | Manual administration and shell automation have been established and infrastructure scale justifies central automation. | Intentionally deferred
FC-004 | Evaluate Stratis Storage Management | Enhancement / Learning | Higher-level storage management could simplify provisioning and management. | Storage administration becomes sufficiently complex to justify another abstraction. | Deferred from DD-004
FC-005 | Dedicated Storage Node | Architecture Enhancement | Separating storage from file services could improve flexibility and future scale. | Capacity, performance, resilience or multi-host storage requirements exceed local-storage model. | Deferred from DD-004
FC-006 | Network Storage using NFS/iSCSI | Architecture Enhancement | Network-presented storage may support workload separation or shared storage. | Dedicated storage tier, clustering, migration or shared-storage requirement emerges. | Not required for v1
FC-007 | Department-Specific Filesystems | Storage Enhancement | Separate filesystems could provide independent recovery, mount policy and capacity boundaries. | Departments develop materially different capacity, security, performance or recovery requirements. | LLD option / future enhancement
FC-008 | Departmental Storage Quotas | Governance / Capacity | Prevent individual departments/users from exhausting shared storage. | Capacity contention or business requirement for defined allocations. | Evaluate during LLD
FC-009 | LVM Thin Provisioning | Storage Optimisation | Could improve flexible allocation of virtual storage. | Large number of volumes or inefficient pre-allocation becomes an operational concern. | Deferred
FC-010 | Storage Snapshot Strategy | Recoverability Enhancement | Snapshots could provide short-term recovery from selected administrative errors. | Requirement for rapid point-in-time rollback emerges. | Evaluate later; not substitute for backup
FC-011 | Cloud File Synchronisation | Integration Enhancement | Selected folders could potentially use cloud versioning/off-site collaboration. | Remote collaboration, external sharing or cloud-versioning requirement emerges. | Deferred
FC-012 | Broader Cloud Storage Integration | Architecture / Expansion | Hybrid/on-premises + cloud storage may become useful as Northwind grows. | Capacity, geographic access, resilience or business cloud strategy changes. | Out of v1 scope
FC-013 | High Availability Compute Platform | Resilience Enhancement | Initial compute design may contain a single-host failure domain. | RTO/availability requirements cannot be achieved through recovery alone. | To be evaluated through resilience decision
FC-014 | Proxmox Cluster | Platform Enhancement | Additional compute hosts could provide management/resilience benefits. | Second/third host introduced or downtime becomes unacceptable. | Future option
FC-015 | VMware/Enterprise Virtualisation Evaluation | Platform / Skills | VMware remains common in enterprise employment environments. | Separate CV/lab learning project or Northwind receives requirement for VMware compatibility. | Rejected for current v1, not permanently
FC-016 | Direct KVM/libvirt Administration | Skills / Platform | Proxmox abstracts some lower-level Linux virtualisation administration. | RHCSA completed or future Linux virtualisation learning project begins. | Deferred learning opportunity
FC-017 | External Services Zone | Security / Network | HLD allows a conditional isolated zone for externally accessible workloads. | Northwind publishes an Internet-facing application or service. | Conditional / not currently required
FC-018 | Enhanced Network Segmentation | Security Enhancement | Additional trust boundaries may eventually improve isolation. | Security review, new workloads or increased risk classification. | Logical segmentation in v1; expand when justified
FC-019 | Dedicated Management Network / Stronger Management Plane Isolation | Security Enhancement | Administrative traffic can be separated more strongly from ordinary service traffic. | Infrastructure scale/security requirements increase or audit finding identifies admin-path risk. | Conceptually designed; implementation depth TBD
FC-020 | Administrative Jump Host | Security Enhancement | Central controlled administrative entry point may strengthen privileged-access management. | Number of managed systems grows or direct administrative access becomes difficult to audit. | Future candidate
FC-021 | Multi-Factor Authentication | Security Enhancement | Adds another control to sensitive/remote/privileged authentication. | Risk assessment, remote-access expansion or compliance requirement. | Future evaluation
FC-022 | Advanced Threat Detection | Security Enhancement | HLD identifies threat detection as a security capability but v1 need not implement a complex security platform. | Security incident, audit requirement or increased exposure. | Scale proportionately
FC-023 | Vulnerability Management Platform | Security / Operations | Structured vulnerability tracking may eventually improve patch/security governance. | Host count increases or security audit demands measurable vulnerability management. | Future enhancement
FC-024 | Centralised Configuration/Asset Database | Operations Enhancement | Initial asset/configuration management can use structured files rather than a full CMDB. | Asset volume, relationships and reporting become difficult to manage manually. | Deferred; simple register first
FC-025 | IT Asset Management Application | Operations Enhancement | Hardware/software/licence lifecycle may outgrow spreadsheet/structured-file management. | Manual asset tracking becomes unreliable or audit requirements grow. | Future project candidate
FC-026 | Automated Joiner/Mover/Leaver Workflow | Process / Automation | User lifecycle requires coordinated HR/IT activities and approvals. | User volume or missed lifecycle actions create operational/security issues. | Initial process manual; automate later
FC-027 | Electronic Approval Workflow | Governance Enhancement | CAP-019 can initially remain procedural rather than requiring a dedicated platform. | Approval volume/auditability makes email/manual workflow inadequate. | Conditional capability
FC-028 | Self-Service Password Reset | IAM Enhancement | Could reduce IT workload for routine authentication resets. | Helpdesk volume becomes significant or central IAM introduced. | Deferred
FC-029 | Enhanced Monitoring Automation | Operations Enhancement | Monitoring responses could eventually trigger automated remediation. | Repetitive, well-understood incidents occur frequently enough to automate safely. | Future maturity step
FC-030 | Monitoring Dashboards / Administrative Visibility | Operations Enhancement | Earlier capability analysis identified a need for administrative visibility/reporting. | Monitoring data becomes distributed or difficult for IT to interpret quickly. | Future enhancement depending on monitoring selection
FC-031 | Advanced Capacity Forecasting | Operations Enhancement | Monthly capacity/performance reporting may eventually mature into trend forecasting. | Infrastructure growth begins approaching resource limits. | Future maturity improvement
FC-032 | Central Log Analytics / SIEM-like Capability | Security / Logging | Centralised logs may eventually require richer search, correlation and detection. | Log volume grows, investigation becomes difficult or security requirements increase. | Start simple; expand when justified
FC-033 | Longer-Term / Off-site Backup Copy | Resilience Enhancement | Protected local backups may still share site-level risks with production. | DR analysis identifies unacceptable site-wide data-loss exposure. | Evaluate in DD-005
FC-034 | Immutable / More Strongly Isolated Backups | Security / Recovery | Protects recovery data from compromise or administrative mistakes. | Threat model includes ransomware/destructive privileged compromise. | Future/possibly DD-005 option
FC-035 | Automated Backup Validation | Operations Enhancement | Successful job status does not prove data is recoverable. | Backup volume grows or manual restore testing becomes burdensome. | Initial restore tests manual; automation later
FC-036 | Secondary Recovery Environment | Disaster Recovery | Some services may eventually need recovery away from the primary compute platform. | Refined RTO/RPO cannot be achieved through rebuild/recovery on primary infrastructure. | Future resilience option
FC-037 | Per-System RTO/RPO Refinement | Governance / Design Debt | Discovery initially captured a generic four-hour recovery target rather than service-specific objectives. | Before final backup/recovery and resilience design. | Outstanding design item
FC-038 | Application-Level Resilience | Resilience Enhancement | Specific business applications may eventually justify redundancy beyond infrastructure recovery. | Business impact analysis identifies critical applications with stringent availability needs. | Proportionate / future decision
FC-039 | Additional Compute Capacity / Cloud Compute | Expansion | Local lab hardware could eventually limit simulated infrastructure growth. | Host resources become constrained during later project expansion. | Fallback option
FC-040 | Additional Northwind Departments / Users | Business Expansion | Lab is intended to evolve as the simulated company grows. | Future project phase/change request. | Planned simulation mechanism
FC-041 | New Internally Hosted Applications | Business Expansion | Application hosting capability allows future business applications to be added when justified. | New departmental/business requirement. | Future project source
FC-042 | Public-Facing Application Hosting | Business Expansion / Security | Would activate currently conditional external-services architecture. | Customer requests Internet-accessible service. | Future project candidate
FC-043 | Formal Software Repository Management | Patch / Operations Enhancement | Package lifecycle could eventually require controlled internal repository/mirroring. | Scale, bandwidth, version consistency or patch governance demands it. | Future maturity step
FC-044 | Automated Patch Deployment | Operations Enhancement | Patch governance may eventually benefit from coordinated automation. | Manual patching becomes repetitive after the process is understood. | Automation after manual process
FC-045 | Rollback/Recovery Improvements for Changes | Operations / Reliability | Controlled and recoverable change is an explicit architecture principle. | Failed patch/configuration change demonstrates weaknesses in rollback process. | Likely source of simulated incidents/improvements
FC-046 | Train-the-Trainer / Enhanced User Documentation | Operational Improvement | Documentation and UAT requirements include enabling Northwind to support/adopt services. | New services, recurring support calls or staff turnover. | Iterative improvement
FC-047 | Configuration Drift Detection | Operations Enhancement | Standardisation becomes harder as system count increases. | Differences between nominally identical hosts start causing incidents. | Excellent later automation project
FC-048 | Automated Compliance / Security Checks | Security Automation | Repeatable host-security checks could reduce configuration drift and audit effort. | Security baseline matures after manual configuration is understood. | Future automation project
FC-049 | Introduction of SUSE Linux Enterprise Server
FC-050 | Future consideration — Dedicated Hypervisor Management Network
FC-051 | Access environment via device from outside network, e.g. public internet not same WIFI