## Workshop 2 Actions Log
ID | Action | Owner | Due
ACT-001 | Update BRD based on Workshop 2 outcomes and issue Version 1.0 for review | Redstone | Next week
ACT-002 | Review and approve BRD v1.0 | Northwind | TBD
ACT-003 | Produce initial asset inventory baseline | Northwind | TBD
ACT-004 | Define initial asset ownership model (Owner, Custodian, Technical Owner) | Northwind | TBD
ACT-005 | Nominate business SMEs for future UAT activities | Northwind | Before design/UAT planning
ACT-006 | Commence HLD activities following BRD approval | Joint | After approval

## Sheet1
Complete | Section / Area | Workshop 2 change | Sarah's email / RHCSA coverage change | v1.0 action
Y | Document Control | BRD approved for baseline after updates | — | Change version to 1.0, update date and revision history
Y | 1. Purpose | BRD now represents completed requirements gathering | — | Clarify that v1.0 establishes the baseline for design
Y | 2. Executive Summary | Reflect Workshop 2 outcomes | Reflect expanded operational capabilities | Rewrite executive summary
Y | 3. Project Description | Incorporate refined requirements | Include improved administration, automation, recovery and operational maturity | Update
Y | 4. Scope | Documentation, asset management, testing and operational processes clarified | Automation, software management, recovery and operational administration | Expand scope where appropriate
Y | 5. Business Drivers | Growth assumptions updated | Operational efficiency strengthened through automation/standardisation | Review/update
| 6. Current State | Asset baseline remains outstanding | — | Record current information without inventing asset figures
| 7. Delivery Approach | Controlled migration, UAT and pre-production testing discussed | Software/update testing reinforced | Update delivery/testing language
| 7. Governance | Formal RTM, change management and acceptance | — | Retain, refine where necessary
| BR-001 Business Service Continuity | Clarify continuity expectations | Recovery requirements reinforced | Review acceptance criteria
| BR-002 Identity Management | HR/IT ownership discussed | — | Refine ownership/process language
| BR-003 User Provisioning | Joiner/mover/leaver process | Automation of repetitive administration | Expand into controlled lifecycle + automation
| BR-004 RBAC | — | Host/resource security reinforced | Review relationship with security requirements
| BR-005 File Services | — | Network resource access | Ensure network-based resource access is explicitly covered
| BR-006 Data Organisation | Naming conventions | — | Retain/update
| BR-007 Data Segregation | — | Security enforcement | Review for host-level access controls
| BR-008 Secure Data Access | — | Security enforcement/auditability | Strengthen where necessary
| BR-009 Centralised Logging | — | Persistent operational logging | Expand requirement to cover log persistence/retention
| BR-010 Monitoring | Split operational monitoring from capacity/performance management | Performance management reinforced | Split/expand requirement
| New – Capacity & Performance | Monthly capacity/performance reporting | Performance identification and remediation | Add new BR
| BR-011 Threat Detection | — | Security controls | Review but don't over-specify technology
| BR-012 Backups | Automated backups | Scheduled administration | Retain + strengthen scheduling
| BR-013 Backup Validation | Recovery testing | System recovery | Expand recovery requirement
| BR-014 Application Resilience | HA remains decision point | — | Do not mandate HA; document as design decision
| BR-015 Remote Administration | — | Administrative capabilities | Retain
| BR-016 Secure Remote Access | Remote/office users should have consistent experience | — | Refine UX requirement
| BR-017 Network Security | Firewall/internet access requirement | Host-level security | Review
| BR-018 Network Segmentation | — | — | Retain
| BR-019 Integration | Microsoft 365 / existing services | — | Review integration wording
| BR-020 Application Hosting | — | — | Retain
| BR-021 Scalability | Growth forecast updated | — | Update five-year assumptions
| BR-022 Standardisation | — | Automation/controlled administration | Strengthen
| BR-023 Documentation | SOPs + runbooks explicitly required | Recovery/troubleshooting procedures | Expand to distinguish SOPs, runbooks and user documentation
| BR-024 Reporting | Operational vs management reporting clarified | Performance/capacity reporting | Refine
| BR-025 Approval Workflows | — | — | Review; avoid unnecessary scope
| BR-026 Print Services | Network printing requirement confirmed | — | Retain
| New – Asset Management | Formal IT asset management introduced | — | Add BR
| New – Software Update Management | Controlled update process + sandbox testing | Software/package lifecycle | Add BR
| New – Joiner/Mover/Leaver Process | Ownership/process clarification | Automation | Add or restructure BR-003
| New – Administrative Automation | — | Explicit automation requirement | Add BR
| New – Scheduled Administration | — | Scheduling of routine tasks | Add BR or incorporate into operational management
| New – System Recovery | RTO/RPO discussion | Boot/configuration/service recovery | Add BR
| New – Time Synchronisation | — | Consistent system time | Add BR
| New – Host Security Enforcement | — | Explicit security enforcement | Add/refine BR
| New – Network Resource Mounting/Access | File services | Automated network resource access | Add if not sufficiently covered by file-services requirement
| NFR-001 Availability | HA decision point | — | Clarify availability expectations without mandating HA
| NFR-002 Reliability | — | Recovery/troubleshooting | Review
| NFR-003 Performance | Capacity/performance discussion | Performance management | Strengthen
| NFR-004 Scalability | Growth updated | — | Update
| NFR-005 Security | — | Host-level security enforcement | Strengthen
| NFR-006 Auditability | — | Persistent logs | Strengthen
| NFR-007 Data Protection | — | — | Retain
| NFR-008 Maintainability | Maintenance process | Automation/scheduling | Strengthen
| NFR-009 Recoverability | 4-hour expectation discussed | System recovery | Major update
| NFR-010 Supportability | SOPs/runbooks | Troubleshooting/recovery documentation | Expand
| NFR-011 Administrative Simplicity | — | Automation | Strengthen
| NFR-012 Compatibility | Existing applications | Software/update testing | Review
| NFR-013 Compliance | — | — | Retain
| NFR-014 Monitoring | Operational monitoring split from capacity | Performance management | Refine
| NFR-015 Extensibility | Future growth | — | Retain
| New NFR – Time Consistency | — | System time | Add if better expressed as NFR
| New NFR – Recovery | 4-hour business expectation | Recovery procedures | Add/strengthen as appropriate
| Assumptions | Asset inventory, SMEs, growth information | — | Update outstanding dependencies
| Constraints | Migration downtime | — | Add migration constraints
| Risks | Migration, update testing, asset information | — | Expand risk register
| Success Criteria | UAT, documentation, operational handover | Expanded operational capability | Update
| Appendix / Priority | MoSCoW confirmed | — | Review priority definitions for consistency

## BRD CRs
Ref | Customer Feedback | Consultant Response | Type | Existing BR? | Action | Status
CR-001 | Clarify business continuity expectations including recovery times, server failures and office outages. | Further discovery required to define Recovery Time Objectives (RTO), Recovery Point Objectives (RPO), acceptable downtime and disaster recovery expectations before solution design. | Clarification | BR-012, BR-013, BR-014, NFR-009 | Schedule Business Continuity Workshop. Update BRD after workshop. | Open
CR-002 | Expand remote working capability so remote staff have an experience comparable to office users. | Requirement accepted. Existing requirement should be expanded to better describe business expectations for remote workers. | Enhancement | BR-016 | Update requirement wording. | Open
CR-003 | Growth forecast revised to approximately 80 users within 3 years and possible second warehouse within 5 years. | Requirement accepted. Growth assumptions require updating and further discovery regarding future sites. | Modification | BR-021, NFR-004 | Update growth assumptions and schedule workshop. | Open
CR-004 | Include operational procedures such as onboarding, password resets, restoring files and common fault resolution. | Requirement accepted. Expand documentation deliverables to include operational runbooks and SOPs. | Enhancement | BR-023, NFR-010 | Update documentation requirements. | Open
CR-005 | Introduce formal IT asset management. | New business requirement identified. | New Requirement | New | Add new BR. | Open
CR-006 | Improve software update process with better consistency and governance. | New operational requirement accepted. Solution approach to be determined during design. | New Requirement | New | Add new BR. | Open
CR-007 | Improve password policy and account security. | Existing security requirements should be expanded to explicitly include password governance. | Enhancement | BR-004, BR-008, NFR-005 | Update existing requirements. | Open
CR-008 | Improve Joiners, Movers and Leavers process. | Existing lifecycle management requirement should be expanded to include departmental transfers and access reviews. | Enhancement | BR-003 | Update requirement wording. | Open
CR-009 | Improve visibility of storage capacity before issues occur. | Existing monitoring requirement should explicitly include storage capacity monitoring and forecasting. | Enhancement | BR-010, BR-024, NFR-014 | Update monitoring requirements. | Open
CR-010 | Clarification regarding implementation downtime. | No BRD change required. Provide response during customer workshop and document implementation strategy within future HLDs and SoWs. | Clarification | None | Respond to customer. | Closed
CR-011 | Clarification regarding staff retraining. | No BRD change required. Confirm knowledge transfer forms part of project deliverables. | Clarification | BR-023 | Respond to customer. | Closed
CR-012 | Clarification regarding prioritisation if budget becomes constrained. | No BRD change required. Explain MoSCoW prioritisation and phased delivery approach. | Clarification | Section 7 | Respond to customer. | Closed

## Decision Points
ID | Decision Point | Northwind Response | Status | Notes
DP-001 | Expected business growth over the next five years | We anticipate growing from approximately 50 employees to between 75–100 employees. We do not currently expect additional office locations but would like any proposed solution to support future expansion if required. | Confirmed | Solution should be scalable.
DP-002 | Business critical services requiring highest availability | ERP/Stock Management, File Services, Microsoft 365 access and Finance systems are considered critical. Extended outages would significantly impact business operations. | Confirmed | Priority for resilience and backup.
DP-003 | Acceptable downtime for critical systems | Ideally less than four hours during business hours. Planned maintenance should occur outside office hours where practical. | Confirmed | To influence DR and maintenance planning.
DP-004 | Remote working requirements | Around 20% of staff work remotely on a regular basis. Secure remote access is required for office staff, management and IT administrators. | Confirmed | Remote access solution required.
DP-005 | Authentication requirements | We would like all staff to have individual accounts. We are interested in Single Sign-On if appropriate but would appreciate your recommendation. | Confirmed | Consultancy recommendation requested.
DP-006 | Multi-Factor Authentication (MFA) | We would like MFA implemented for remote access, administrator accounts and any systems containing sensitive company data. | Confirmed | Security requirement.
DP-007 | Password policy | Happy to adopt industry best practice. We would welcome your recommendations. | Confirmed | Consultancy to propose policy.
DP-008 | Department file permissions | HR and Finance data should remain confidential. Other departmental information should be shared internally where appropriate. Management require access across all departments. | Confirmed | RBAC requirements.
DP-009 | Future cloud strategy | We are happy to continue using Microsoft 365 but would prefer core business systems and company data to remain under our control unless there is a compelling business reason to use cloud services. | Confirmed | Hybrid approach preferred.
DP-010 | Backup retention requirements | Daily backups with the ability to restore previous versions where possible. Financial records should be retained for at least seven years. | Confirmed | Legal retention requirement.
DP-011 | Disaster Recovery expectations | We expect to recover essential business operations within one business day following a major incident. | Confirmed | RTO requirement.
DP-012 | Security monitoring | We do not currently have formal monitoring but would like recommendations on how best to improve visibility into security events. | Confirmed | Opportunity for future project.
DP-013 | Patch management | We'd prefer updates to be scheduled monthly, with critical security patches applied sooner if necessary. | Confirmed | Maintenance window required.
DP-014 | Preferred maintenance window | Tuesday or Thursday evenings after 18:00 are preferred to minimise disruption. | Confirmed | To be reflected in operational procedures.
DP-015 | High Availability | We'd like to understand the additional cost before deciding whether High Availability is required. | To Be Confirmed | Cost/benefit discussion required.
DP-016 | Guest Wi-Fi requirements | Yes. Guest access should be isolated from the corporate network. | Confirmed | Networking requirement.
DP-017 | Bring Your Own Device (BYOD) | Personal devices may access email only. Company files and internal systems should remain accessible only from managed devices. | Confirmed | Security policy.
DP-018 | Mobile device management | Not currently required, although this may become necessary as the business grows. | Deferred | Future consideration.
DP-019 | Reporting requirements | Management would appreciate simple reporting showing system health, backup status and security alerts. | Confirmed | Operational reporting.
DP-020 | Preferred implementation approach | We'd prefer a phased implementation to minimise operational disruption. Any business-critical changes should be performed outside trading hours. | Confirmed | Delivery strategy agreed.
DP-021 | Budget expectations | We have an approved budget for modernisation but would like to review costs on a phase-by-phase basis before committing to implementation. | Confirmed | Supports phased SOWs.
DP-022 | User training requirements | Basic end-user training and administrator documentation would be beneficial. | Confirmed | Training to be included in project scope.
DP-023 | Compliance requirements | We handle customer personal information and therefore require compliance with UK GDPR and general cybersecurity best practices. | Confirmed | Compliance consideration.
DP-024 | Future business priorities | Our immediate priorities are improving resilience, simplifying administration and reducing operational risk rather than implementing the latest technology. | Confirmed | Helps guide design decisions.
DP-025 | Final approval authority | Final approval for major project decisions will be provided jointly by the Operations Director and Finance Manager. | Confirmed | Governance agreed.

## CR-001
Business System | Business Impact | Target RTO | Target RPO | Business Rationale | Notes
File Storage / Shared Documents | High | 4 hours | 1 hour | Staff rely on shared documents throughout the day. Losing more than an hour's work would be frustrating.
Microsoft 365 (Email & Teams) | Medium | Vendor Managed | Vendor Managed | As this is cloud-hosted, we'd expect Microsoft to provide resilience rather than us.
Internal Authentication / User Services | High | 4 hours | 1 hour | Staff need to be able to log in to work.
Internal Applications (future systems) | High | 4 hours | 1 hour | Any business applications we'd expect to recover within the working day.
Printing Services | Low | Next Business Day | 24 hours | Printing is useful but not business critical.
Internal Website / Intranet | Low | Next Business Day | 24 hours | Staff can cope without it for a while.
Monitoring & Logging | Medium | 24 hours | 24 hours | We'd like it back quickly, but it's not operationally critical.
Outcome |  | Notes
Northwind confirmed that RTO/RPO values relate to restoration of business services following major outages rather than routine IT support incidents. Critical services (file storage, authentication, future business applications) require an RTO of 4 hours and an RPO of 1 hour. Lower-priority services may have longer recovery objectives. Increased business impact during seasonal trading periods should be considered during solution design and disaster recovery planning. |  | As for data loss, we'd really like to avoid losing more than about an hour's worth of work. Anything beyond that and departments would have to recreate documents, which is both time-consuming and frustrating.
If our file server was unavailable for half a day, business would start grinding to a halt. People couldn't access quotations, HR documents, finance spreadsheets or operational procedures. Four hours feels like a reasonable maximum before it starts having a significant financial impact.
One thing I'd add is that our busiest periods tend to be around seasonal promotions and the run-up to Christmas. If we suffered a major outage during those periods, the business impact would be considerably greater than at quieter times. We don't necessarily expect different recovery targets, but it's probably something worth documenting as part of the risk assessment."

## CR-004
Audience | Documentation Type | Purpose
End Users | User Guides / Quick Reference Guides | How to perform daily tasks
Department Managers / Process Owners | Process Documentation | How business processes work after changes
IT / Administrators | SOPs / Runbooks / Technical Documentation | How to operate, maintain, troubleshoot, and recover systems
New Wording | Northwind requires sufficient documentation to support effective operation, maintenance, user adoption, and future support of implemented solutions.
Document Ownership
Item | Decision
Documentation created during project | Redstone
Documentation validated during UAT | Joint
Documentation ownership after handover | To be confirmed during design/support model definition
Documentation updates after project closure | Managed through change management process

## CR-005
Northwind requires a formal asset management capability to provide visibility, accountability, lifecycle management and reporting for IT assets.
For asset management, I think our main reporting needs would be:
complete list of assets;
who owns each asset;
where each asset is located;
warranty and replacement information;
software/licence information where relevant;
assets approaching end of life.
I don't think we need daily reports sent to management. That would probably create noise. But having the information available and being able to produce reports when needed would be valuable.
Asset Category | Current Estimate | Notes
Employees / Users | ~50 | Expected to grow over the next 5 years
Company laptops / desktops | ~55 | Includes some shared operational devices
Mobile devices | ~20 | Mostly company phones/tablets
Servers | 4 | Combination of physical and virtual systems
Network devices | ~15 | Switches, firewalls, wireless equipment
Printers / MFP devices | ~8 | Distributed across departments
Business applications | ~10 | Mix of cloud services and internally hosted applications
SaaS platforms | ~8 | Microsoft 365 plus other specialist services

## CR-006
For patch management, we'd probably want:
what systems have been patched;
what updates are outstanding;
any failed updates;
systems that are vulnerable or out of date;
confirmation that critical updates have been applied
I don't think we need daily reports sent to management. That would probably create noise. But having the information available and being able to produce reports when needed would be valuable.
New wording: Requirement: Controlled Software Update and Change Management Process. Northwind requires a structured process for identifying, testing, approving, deploying, and validating software updates and configuration changes to reduce operational risk.
Acceptance criteria:
Updates can be assessed before production deployment.
Critical updates can be prioritised appropriately.
Testing procedures exist for significant changes.
Deployment outcomes can be verified.
Failed changes have documented recovery procedures.

## CR-007
Outcome:
Authentication requirements are confirmed as a business requirement rather than a technology requirement.
Redstone to evaluate authentication and password management options during the design phase.
HR will initiate joiner/mover/leaver processes, while IT will administer user accounts and authentication services.
Password reset approach (IT-managed vs. self-service) to be evaluated during solution design.
The proposed solution should be secure, scalable, and proportionate to Northwind's size and expected growth.
For example:
new starter request;
account creation;
equipment assignment;
role changes;
department transfers;
leavers;
temporary access;
password resets;
privileged accounts.
At the moment those processes are handled slightly differently depending on who is involved.

## CR-009
Requirement | Primary Audience | Business Outcome
Operational Monitoring | IT Operations | Detect and resolve issues proactively to maintain service availability.
Capacity & Performance Management | IT Leadership / Business Leadership | Provide trend analysis and operational insights to support planning, budgeting, and continual improvement.

## CR-010
Northwind prefers a risk-based transition approach. The selected migration method should be determined during the design phase based on system criticality, business impact, complexity, data integrity requirements, and rollback considerations.
Generally we can adjust the migration process based on the Sow, likewise bug fixes and items coming under support may require immediate deployment to production and other small changes may get deployed as part of a weekly "patch Tuesday" deployment where small changes can be deployed in a controlled way. What we are talking about in many ways is for larger projects, how are the features "rolled out" - all departments at once "big bang" or incrementally. As stated I think we can address this in the Sow. By specifying what is in and out of scope.

## CR-011
So your process becomes:
1. Northwind nominates SMEs.
2. Redstone implements the solution in the sandbox.
3. Redstone works closely with the SMEs during UAT.
4. UAT scripts validate both the solution and the supporting documentation.
5. Feedback is incorporated before go-live.
6. SMEs lead knowledge transfer within their departments.
7. Redstone completes handover and provides post-implementation support as agreed.

## DP-015
Original Decision Required:
Determine whether Northwind requires high availability capabilities and understand associated investment.
Outcome:
Northwind requires Redstone to evaluate availability and resilience options during the design phase. Options should be assessed against business criticality, operational impact, recovery objectives, implementation cost, and ongoing operational requirements.
Decision Status:
✅ Resolved – Deferred to Design Phase
Design Inputs:
Business criticality classification.
Agreed RTO/RPO objectives.
Impact of service interruption.
Capital investment considerations.
Ongoing operational costs.