## Design Decision Register
Decision ID | Decision Area | Business / Architecture Driver | Options Considered | Evaluation Criteria | Recommended Option | Rationale | Risks / Trade-offs | Decision Owner | Status | Notes
DD-001 | Compute / Virtualisation | CAP-015 Compute Provisioning / Hosting; CAP-010 Application Hosting; requirements for infrastructure scalability, standardisation, recoverability and supportability; CON-005 Operational Consistency; CON-011 Scalable Without Unnecessary Complexity; CON-012 Supportable & Maintainable Design; DP-002 Prefer Simplicity; DP-003 Standardise Where Practical; DP-013 Design for Managed Growth; v1 focus on Linux/RHCSA administration. | 1. KVM + libvirt — direct Linux virtualisation stack managed through Linux tooling/APIs. 2. Proxmox VE — integrated virtualisation management platform built around KVM and related open-source technologies. 3. VMware/ESXi — established enterprise virtualisation platform; retained as a comparison option but not preferred for v1 due to licensing/access considerations and project fit. | Requirements/capability fit; deployment complexity; administrative overhead; Linux/RHCSA learning alignment; workload isolation; scalability; recoverability; hardware compatibility; management usability; cost/licensing; supportability; ability to expand the lab later. | Proxmox VE | Proxmox provides the required virtualised compute capability while offering an integrated management layer that reduces the effort required to build and operate the virtualisation platform itself. It uses KVM for virtual-machine virtualisation, retaining exposure to Linux virtualisation concepts while avoiding the additional complexity of designing and administering a raw KVM/libvirt environment. This allows v1 effort to remain focused on administering the Linux workloads hosted by the platform and meeting RHCSA-oriented project objectives. Proxmox also provides a practical path for future expansion without requiring commercial virtualisation licensing for the planned lab environment. | Direct KVM/libvirt would provide greater exposure to lower-level Linux virtualisation administration and may therefore offer additional learning value. Using Proxmox abstracts some of this complexity behind an integrated management platform. Proxmox-specific administration also introduces platform knowledge outside the core RHCSA objectives. A single-host initial deployment would remain a compute SPOF unless additional resilience is introduced; this should be assessed separately under the Availability/Resilience decision. | Redstone Consulting — recommendation; Northwind Outdoor Ltd. — approval | Proposed | Direct KVM/libvirt administration is deferred from the initial Northwind implementation because the additional virtualisation-platform engineering would dilute the v1 focus on Linux systems administration and RHCSA objectives. KVM/libvirt may be introduced through a future lab exercise or change request once the core environment is operational.
DD-002 | Identity & Access Management Architecture | CAP-001 Identity & Access Management; CAP-016 Systems Administration & Management; requirements for user lifecycle management, role-based access, secure data access and administrative access; Security, Maintainability and Operational Consistency NFRs; CON-002 Least-Privilege Access; CON-005 Operational Consistency & Standardisation; CON-012 Supportable & Maintainable Design; DP-002 Prefer Simplicity; DP-003 Standardise Where Practical; DP-006 Enforce Least Privilege; DP-009 Treat Administrative Access as a Controlled Service; DP-015 Prefer Automation for Repeatable Operations, Not Understanding Replacement. | 1. Local Linux IAM — identities, groups, permissions and privileged access maintained independently on each Linux host using native Linux mechanisms. 2. Local Linux IAM with centralised automation — retain local identities while using automation to distribute and maintain standardised account/group/access configuration across systems. 3. Centralised IAM — introduce a shared directory/identity service providing central authentication and identity lifecycle management across supported systems. | Requirements fit; security and least privilege; RHCSA learning alignment; implementation complexity; administrative overhead; user lifecycle management; consistency across systems; scalability; supportability; recoverability; automation potential; risk of configuration/account drift; suitability for Northwind v1 scale. | Local Linux IAM for v1, initially administered manually using documented standards, with repeatable account-management activities subsequently automated where appropriate. Centralised IAM deferred for later reassessment. | Native Linux identities, groups, ownership, permissions and privilege mechanisms provide sufficient IAM functionality for the initial Northwind environment while maintaining a strong focus on core Linux administration skills. Manual implementation initially ensures administrators understand account creation, group membership, UID/GID management, permissions, password/account controls and privileged access before automation is introduced. Standardised procedures and later automation can reduce configuration drift and administrative effort without introducing the additional infrastructure and operational complexity of a central directory service during v1. Centralised IAM remains architecturally valid for future expansion and should be reconsidered if scale, security or lifecycle-management requirements make distributed local accounts operationally inefficient. | Local identities must be maintained across multiple systems, increasing administrative effort as the environment grows. Account, UID/GID, group and privilege configuration may drift between hosts if standards are not followed. Joiner/mover/leaver processes must ensure accounts are updated or disabled on every applicable system, creating a risk of orphaned accounts. Automation can reduce these risks but does not provide true central authentication and introduces its own operational dependency. Centralised IAM may therefore become preferable as Northwind's infrastructure grows. | Redstone Consulting — recommendation; Northwind Outdoor Ltd. — approval | Proposed | if host/user numbers, joiner-mover-leaver workload, identity drift, security risk, or administrative effort become unacceptable, Northwind should reassess centralised IAM.
DD-003 | File & Data Services Architecture | CAP-003 File & Data Services; CAP-001 Identity & Access Management; CAP-004 Storage Provisioning & Management; requirements for secure file services, structured data organisation, departmental data segregation and secure data access; Data Protection, Security, Recoverability and Operational Consistency NFRs; CON-002 Least-Privilege Access; CON-005 Operational Consistency & Standardisation; CON-013 Business Data Segregation & Protection; DP-002 Prefer Simplicity; DP-003 Standardise Where Practical; DP-006 Enforce Least Privilege; DP-012 Avoid Unnecessary Coupling; DP-017 Protect Business Data Throughout its Lifecycle. | 1. Consolidated Linux file-services node — a Linux server provides appropriate file-sharing services directly to supported clients, with native Linux permissions and access-control mechanisms protecting departmental data. 2. Separated storage and file-services architecture — dedicated storage services provide storage to a separate file-services node, which provides client-facing file access and access controls. 3. Cloud-integrated file services — locally hosted file services combined with cloud-based synchronisation/versioning for selected business data. | Business requirements fit; Windows/Linux client interoperability; security and departmental segregation; least-privilege enforcement; operational complexity; supportability; recoverability; scalability; failure dependencies; administrative overhead; RHCSA/Linux learning alignment; integration with IAM; integration with backup/recovery; future extensibility. | Consolidated Linux file-services architecture using appropriate Linux/Windows-compatible file-sharing protocols and native Linux access controls, backed by managed persistent storage. | A consolidated Linux file-services architecture satisfies Northwind's current requirements for shared file access, structured departmental data and controlled access without introducing an unnecessary separate storage-services tier. The architecture supports Linux-native ownership, group permissions, ACLs and host security controls while allowing appropriate file-sharing protocols to support both Linux and Windows clients. It provides strong alignment with the v1 Linux/RHCSA learning objectives while maintaining a comparatively simple and supportable operational model. Storage implementation is intentionally treated as a separate architectural decision. | Combining file-service functionality on a single logical service node creates a service dependency and potential single point of failure unless resilience or recovery controls mitigate the risk. Native access controls and client-facing file-sharing configuration must remain aligned to prevent unintended access. As data volumes, performance requirements or availability requirements increase, separation of storage and file-service responsibilities may become justified. Cloud integration is deferred and may require future reassessment if Northwind develops requirements for external collaboration, cloud-based versioning or additional off-site data capabilities. | Redstone Consulting — recommendation; Northwind Outdoor Ltd. — approval | Proposed
DD-004 | Storage Architecture | CAP-004 Storage Provisioning & Management; CAP-003 File & Data Services; CAP-007 Backup & Recovery; requirements for structured data organisation, departmental data segregation, capacity management, recoverability and infrastructure scalability; Performance, Scalability, Data Protection, Recoverability and Operational Consistency NFRs; CON-003 Recoverable Operations; CON-005 Operational Consistency & Standardisation; CON-011 Scalable Without Unnecessary Complexity; CON-012 Supportable & Maintainable Design; CON-013 Business Data Segregation & Protection; CON-014 Capacity & Performance Visibility; DP-002 Prefer Simplicity; DP-003 Standardise Where Practical; DP-004 Design for Recoverability; DP-013 Design for Managed Growth; DP-016 Design for Supportability; DP-017 Protect Business Data Throughout its Lifecycle. | 1. Locally presented LVM-backed XFS storage — managed block storage is presented directly to the workload, with LVM providing flexible logical storage management and XFS providing the filesystem layer. 2. Higher-level Linux storage management — use a storage-management abstraction such as Stratis to simplify provisioning and lifecycle operations. 3. Dedicated storage-services architecture — separate storage and file-service responsibilities, with a storage node providing storage over the network to client workload nodes. 4. Cloud-integrated storage — supplement local storage with synchronised or cloud-hosted storage services for selected data. | Requirements fit; capacity growth; storage isolation; recoverability; operational complexity; performance; scalability; supportability; filesystem flexibility; quota capability; snapshot/recovery options; failure dependencies; RHCSA/Linux learning alignment; integration with file services; integration with backup/recovery; future extensibility. | Locally presented LVM-backed XFS storage for v1, with business data logically separated and separate filesystems introduced only where capacity, recovery, security or operational isolation requirements justify them. A dedicated storage-services node and higher-level storage-management abstraction are deferred. | LVM and XFS provide a mature and flexible Linux-native storage architecture that supports Northwind's current capacity, growth, organisation and recoverability requirements without introducing an unnecessary network-storage tier. LVM provides controlled allocation and expansion of storage while XFS provides a robust filesystem suited to the planned Linux environment. The architecture also strongly supports v1 Linux/RHCSA learning objectives by exposing administrators directly to logical volumes, filesystems, mounts, capacity management and storage troubleshooting. Departmental organisation does not itself require a filesystem per department; the final logical-volume and filesystem layout will therefore be determined during LLD based on capacity, recovery and isolation requirements. | Locally presented storage creates a dependency on the workload/compute environment and does not provide the separation available from dedicated network storage. Poor initial volume sizing may require later capacity changes. Multiple departmental filesystems would provide stronger storage-level isolation but increase administration and may create inefficient capacity allocation. LVM snapshots can assist some operational recovery scenarios but do not replace independent backups. Deferring a dedicated storage tier limits some future scalability and resilience options but avoids unnecessary v1 complexity. | Redstone Consulting — recommendation; Northwind Outdoor Ltd. — approval | Proposed
DD-005 | Backup & Recovery Architecture | CAP-007 Backup & Recovery; CAP-003 File & Data Services; CAP-004 Storage Provisioning & Management; CAP-015 Compute Provisioning / Hosting; requirements for business continuity backups, backup validation and recovery testing, service recovery and recoverable operations; Availability, Reliability, Data Protection and Recoverability NFRs; CON-003 Recoverable Operations; CON-004 Proportionate Availability & Resilience; CON-008 Controlled & Recoverable Change; CON-013 Business Data Segregation & Protection; DP-004 Design for Recoverability; DP-005 Apply Proportionate Resilience; DP-010 Prefer Controlled & Reversible Change; DP-017 Protect Business Data Throughout its Lifecycle. | 1. Native/simple Linux backup architecture — scheduled file and configuration backups using Linux-native mechanisms and protected storage. 2. Dedicated backup service — central backup service/repository providing managed protection, retention and recovery of supported workloads. 3. Layered backup & recovery architecture — short-term point-in-time recovery mechanisms combined with a dedicated backup service using protected backup storage and a secondary copy outside the primary production failure domain. | Business requirements fit; RPO/RTO capability; protection against accidental deletion, corruption, administrative error, workload loss, storage failure and infrastructure failure; recovery granularity; backup isolation; security; recoverability; restore testing; retention capability; operational complexity; monitoring/reporting; storage requirements; scalability; supportability; Linux/RHCSA learning alignment; integration with compute, storage and file services. | Layered backup and recovery architecture comprising short-term point-in-time recovery mechanisms, a dedicated backup service using protected backup storage, and a secondary backup copy maintained outside the primary production failure domain. Backup effectiveness will be validated through scheduled restore testing and documented recovery procedures. | A layered architecture provides protection against a broader range of failure scenarios than any single backup mechanism. Short-term point-in-time recovery provides rapid rollback for appropriate operational errors or changes, while an independent backup service and protected repository provide recoverability following data corruption, workload loss or production-storage failure. A secondary copy outside the primary failure domain provides additional protection against loss of the primary compute/storage environment. The approach supports protection at appropriate levels, including business data, system/configuration data and recoverable workload state, while allowing recovery methods and schedules to be aligned with Northwind's RPO/RTO requirements. Scheduled restore testing ensures that backup success is demonstrated through actual recoverability rather than backup-job status alone. | The layered architecture introduces additional infrastructure, storage consumption and administrative overhead compared with a simple backup approach. Snapshots or other point-in-time mechanisms remain dependent on their underlying storage and must not be treated as independent backups. A remote secondary copy does not automatically provide protection against malicious deletion or ransomware unless appropriate isolation, credentials and access controls are implemented. Backup capacity will increase according to protected data volume, backup frequency and retention requirements. Recovery procedures must be maintained and tested. Service-specific RPO/RTO values remain to be refined and may affect the eventual backup schedules, retention and recovery mechanisms selected during LLD. | Redstone Consulting — recommendation; Northwind Outdoor Ltd. — approval | Proposed
DD-006 | Monitoring & Alerting Architecture | CAP-006 Infrastructure Monitoring & Alerting; CAP-012 Reporting; CAP-015 Compute Provisioning / Hosting; CAP-016 Systems Administration & Management; requirements for operational monitoring and alerting, capacity and performance management, reporting and visibility, service recovery and incident investigation/troubleshooting; Availability, Reliability, Performance, Supportability and Monitoring & Observability NFRs; CON-006 Observable & Auditable Operations; CON-012 Supportable & Maintainable Design; CON-014 Capacity & Performance Visibility; DP-008 Make Operations Observable & Auditable; DP-013 Design for Managed Growth; DP-016 Design for Supportability. | 1. Native/decentralised Linux monitoring — administrators use native Linux tools, scripts and scheduled checks to assess individual host and service health. 2. Dedicated central monitoring platform — infrastructure and service telemetry is collected centrally to provide continuous visibility, alerting, historical data and reporting. 3. Hybrid monitoring architecture — centralised monitoring provides continuous visibility, alerting, historical trends and capacity reporting, while native Linux tools remain available for detailed host-level diagnosis and troubleshooting. | Requirements fit; infrastructure and service visibility; proactive fault detection; service-health monitoring; alerting and escalation capability; historical metric retention; capacity/performance trending; reporting capability; Linux/RHCSA learning alignment; troubleshooting capability; operational complexity; security; scalability; supportability; monitoring-platform dependencies; integration with backup, compute, storage, networking and future application services. | Hybrid monitoring architecture consisting of a centralised monitoring and alerting service providing infrastructure and service health visibility, historical capacity/performance data, configurable threshold-based alerting and operational reporting across supported systems. Native Linux diagnostic and troubleshooting tools will remain the primary mechanism for detailed host-level investigation. | A hybrid approach provides Northwind with central operational visibility while preserving direct Linux administration and troubleshooting capability. Central monitoring enables proactive detection of host, service, storage, backup, network and resource issues; maintains historical data for capacity and performance analysis; and allows alerts to be routed to IT when defined warning or critical conditions occur. Native Linux tools complement this capability by enabling administrators to investigate the underlying cause of detected conditions directly on affected systems. This approach satisfies Northwind's monitoring, reporting and capacity-management requirements without making the monitoring platform a replacement for administrator understanding of the underlying Linux systems. | A central monitoring service introduces an additional infrastructure component that must itself be secured, patched, backed up and maintained. Failure of the monitoring platform may reduce operational visibility and create a monitoring blind spot; appropriate health checks or independent operational controls should therefore be considered. Excessive or poorly configured thresholds may cause alert fatigue, while insufficient thresholds may allow significant conditions to go undetected. Collection and retention of detailed historical metrics will consume storage and compute resources. Agent versus agentless collection, metric retention periods, thresholds, alert-routing mechanisms and monitoring-platform technology remain to be determined during subsequent design activities. | Redstone Consulting — recommendation; Northwind Outdoor Ltd. — approval | Proposed

## Sheet1
Field | DD-006 | Field | Decision ID | Decision Area | Business / Architecture Driver | Options Considered | Evaluation Criteria | Recommended Option | Rationale | Risks / Trade-offs | Decision Owner / Approver | Status
Decision ID | DD-006 | DD-006 | DD-006 | Monitoring & Alerting Architecture | CAP-006 Infrastructure Monitoring & Alerting; CAP-012 Reporting; CAP-015 Compute Provisioning / Hosting; CAP-016 Systems Administration & Management; requirements for operational monitoring and alerting, capacity and performance management, reporting and visibility, service recovery and incident investigation/troubleshooting; Availability, Reliability, Performance, Supportability and Monitoring & Observability NFRs; CON-006 Observable & Auditable Operations; CON-012 Supportable & Maintainable Design; CON-014 Capacity & Performance Visibility; DP-008 Make Operations Observable & Auditable; DP-013 Design for Managed Growth; DP-016 Design for Supportability. | 1. Native/decentralised Linux monitoring — administrators use native Linux tools, scripts and scheduled checks to assess individual host and service health. 2. Dedicated central monitoring platform — infrastructure and service telemetry is collected centrally to provide continuous visibility, alerting, historical data and reporting. 3. Hybrid monitoring architecture — centralised monitoring provides continuous visibility, alerting, historical trends and capacity reporting, while native Linux tools remain available for detailed host-level diagnosis and troubleshooting. | Requirements fit; infrastructure and service visibility; proactive fault detection; service-health monitoring; alerting and escalation capability; historical metric retention; capacity/performance trending; reporting capability; Linux/RHCSA learning alignment; troubleshooting capability; operational complexity; security; scalability; supportability; monitoring-platform dependencies; integration with backup, compute, storage, networking and future application services. | Hybrid monitoring architecture consisting of a centralised monitoring and alerting service providing infrastructure and service health visibility, historical capacity/performance data, configurable threshold-based alerting and operational reporting across supported systems. Native Linux diagnostic and troubleshooting tools will remain the primary mechanism for detailed host-level investigation. | A hybrid approach provides Northwind with central operational visibility while preserving direct Linux administration and troubleshooting capability. Central monitoring enables proactive detection of host, service, storage, backup, network and resource issues; maintains historical data for capacity and performance analysis; and allows alerts to be routed to IT when defined warning or critical conditions occur. Native Linux tools complement this capability by enabling administrators to investigate the underlying cause of detected conditions directly on affected systems. This approach satisfies Northwind's monitoring, reporting and capacity-management requirements without making the monitoring platform a replacement for administrator understanding of the underlying Linux systems. | A central monitoring service introduces an additional infrastructure component that must itself be secured, patched, backed up and maintained. Failure of the monitoring platform may reduce operational visibility and create a monitoring blind spot; appropriate health checks or independent operational controls should therefore be considered. Excessive or poorly configured thresholds may cause alert fatigue, while insufficient thresholds may allow significant conditions to go undetected. Collection and retention of detailed historical metrics will consume storage and compute resources. Agent versus agentless collection, metric retention periods, thresholds, alert-routing mechanisms and monitoring-platform technology remain to be determined during subsequent design activities. | Redstone Consulting — recommendation; Northwind Outdoor Ltd. — approval | Proposed
Decision Area | Monitoring & Alerting Architecture
Business / Architecture Driver | CAP-006 Infrastructure Monitoring & Alerting; CAP-012 Reporting; CAP-015 Compute Provisioning / Hosting; CAP-016 Systems Administration & Management; requirements for operational monitoring and alerting, capacity and performance management, reporting and visibility, service recovery and incident investigation/troubleshooting; Availability, Reliability, Performance, Supportability and Monitoring & Observability NFRs; CON-006 Observable & Auditable Operations; CON-012 Supportable & Maintainable Design; CON-014 Capacity & Performance Visibility; DP-008 Make Operations Observable & Auditable; DP-013 Design for Managed Growth; DP-016 Design for Supportability.
Options Considered | 1. Native/decentralised Linux monitoring — administrators use native Linux tools, scripts and scheduled checks to assess individual host and service health. 2. Dedicated central monitoring platform — infrastructure and service telemetry is collected centrally to provide continuous visibility, alerting, historical data and reporting. 3. Hybrid monitoring architecture — centralised monitoring provides continuous visibility, alerting, historical trends and capacity reporting, while native Linux tools remain available for detailed host-level diagnosis and troubleshooting.
Evaluation Criteria | Requirements fit; infrastructure and service visibility; proactive fault detection; service-health monitoring; alerting and escalation capability; historical metric retention; capacity/performance trending; reporting capability; Linux/RHCSA learning alignment; troubleshooting capability; operational complexity; security; scalability; supportability; monitoring-platform dependencies; integration with backup, compute, storage, networking and future application services.
Recommended Option | Hybrid monitoring architecture consisting of a centralised monitoring and alerting service providing infrastructure and service health visibility, historical capacity/performance data, configurable threshold-based alerting and operational reporting across supported systems. Native Linux diagnostic and troubleshooting tools will remain the primary mechanism for detailed host-level investigation.
Rationale | A hybrid approach provides Northwind with central operational visibility while preserving direct Linux administration and troubleshooting capability. Central monitoring enables proactive detection of host, service, storage, backup, network and resource issues; maintains historical data for capacity and performance analysis; and allows alerts to be routed to IT when defined warning or critical conditions occur. Native Linux tools complement this capability by enabling administrators to investigate the underlying cause of detected conditions directly on affected systems. This approach satisfies Northwind's monitoring, reporting and capacity-management requirements without making the monitoring platform a replacement for administrator understanding of the underlying Linux systems.
Risks / Trade-offs | A central monitoring service introduces an additional infrastructure component that must itself be secured, patched, backed up and maintained. Failure of the monitoring platform may reduce operational visibility and create a monitoring blind spot; appropriate health checks or independent operational controls should therefore be considered. Excessive or poorly configured thresholds may cause alert fatigue, while insufficient thresholds may allow significant conditions to go undetected. Collection and retention of detailed historical metrics will consume storage and compute resources. Agent versus agentless collection, metric retention periods, thresholds, alert-routing mechanisms and monitoring-platform technology remain to be determined during subsequent design activities.
Decision Owner / Approver | Redstone Consulting — recommendation; Northwind Outdoor Ltd. — approval
Status | Proposed

## Glossary
Field | Definition | Guidance / Expected Content
Decision ID | Unique identifier assigned to each architectural decision. | Use a consistent format such as DD-001, DD-002, DD-003. The ID should remain unchanged even if the decision is subsequently revised.
Decision Area | Short description of the architectural subject requiring a decision. | Examples: Compute / Virtualisation Platform, Identity & Access Architecture, Backup & Recovery Architecture. This tells the reader what is being decided.
Business / Architecture Driver | Identifies the requirements, capabilities, constraints or design principles that make the decision necessary and influence its outcome. | Reference relevant BR/NFR IDs, CAP IDs, CON IDs and DP IDs where practical. This provides traceability back to the work already completed.
Options Considered | Records the realistic architectural or technology approaches evaluated for the decision. | Include credible alternatives rather than only the preferred solution. For example: Proxmox VE / VMware ESXi / physical deployment. Options that are clearly unsuitable can still be recorded if there is value in documenting why they were rejected.
Evaluation Criteria | Defines the factors against which the options will be assessed. | Examples include requirements fit, security, recoverability, complexity, maintainability, scalability, cost, skills, hardware requirements and operational overhead. Criteria should derive primarily from Northwind's requirements, constraints and principles.
Recommended Option | Records the option that the design assessment recommends for Northwind. | This is the proposed architectural choice prior to approval. It should identify the option clearly without repeating the full rationale.
Rationale | Explains why the recommended option is preferred over the alternatives. | Capture the important reasoning: which requirements it satisfies, why it scores better against the evaluation criteria, and why rejected alternatives were less suitable. Someone reading this months later should be able to understand why we made the decision.
Risks / Trade-offs | Records disadvantages, limitations, dependencies or risks introduced by the recommended option. | No architecture decision is automatically perfect. Examples: single-host failure risk, additional administration, licensing cost, skills requirement, migration complexity, vendor dependency. Where appropriate, identify how the risk could be mitigated.
Status | Indicates where the decision currently sits in its lifecycle. | I suggest controlled values such as Draft → Proposed → Approved → Superseded. You could additionally use Rejected where appropriate.