## Tasklist
ID | Task | Complete | Comments
1 | Confirm the HLD scope: all approved BRD/RTM requirements are in scope for architectural consideration, even if implementation happens later. | Yes
2 | Group RTM requirements into capability areas - see Architecture domains worksheet in RTM | Yes
3 | Build a dependency map showing which capabilities rely on others. This is HLD-DEP-001 Service Dependency Diagram For example, file permissions depend on identity; identity depends heavily on DNS; monitoring depends on network connectivity and name resolution.
4 | Define a small set of design principles. Examples: centralise administration where practical, separate user/server/management traffic, avoid single points of failure for critical services where justified, test changes in sandbox first, use least privilege, design for expected growth.
5 | Produce an initial “whole environment” conceptual architecture before designing individual services.
6 | Design the logical network: security zones, VLAN purpose, server/user/management separation, firewall boundaries, remote-access path. Do not worry about exact IP addresses yet unless they are needed to validate the concept.
7 | Design the compute model: what major server roles are required, which can share infrastructure, which should be separated, and what will be virtualised.
8 | Design identity and access: where accounts live, how Linux systems authenticate users/admins, how groups map to access, how joiners/leavers affect access, and where Microsoft 365 fits.
9 | Design core infrastructure services such as DNS, DHCP, time synchronisation, file services, printing, internal applications, and remote administration.
10 | Design storage at a high level: local versus shared storage, expected capacity, growth, filesystem needs, and which workloads require separate storage.
11 | Design backup and recovery: what is protected, approximate backup frequency, retention principles, recovery order, RPO/RTO alignment, and where restore testing happens.
12 | Design security architecture: trust boundaries, administrative access, least privilege, firewall philosophy, SELinux posture, logging, patching, and secrets/password handling.
13 | Design monitoring and logging: what needs monitoring, where logs go, how alerts reach IT, what is operational monitoring versus monthly capacity reporting.
14 | Review resilience and failure scenarios: DNS failure, file server failure, hypervisor failure, storage exhaustion, firewall outage, failed patching, failed backup.
15 | Record major choices requiring justification as ADR candidates rather than burying the rationale inside the HLD.
16 | Map every RTM requirement to at least one HLD section, design component, or explicit statement that it requires no architectural treatment.
17 | Review the complete design for contradictions and missing dependencies.
18 | Only after the HLD is stable, split implementation into SoWs/sprints and develop the LLDs.

## Expected Outputs
Diagram | What it should answer
HLD-ARC-001 Overall Solution Architecture | What are the major components of the Northwind environment and how do they relate?
HLD-NET-001 Logical Network Architecture | What networks/security zones exist and how does traffic flow between them?
HLD-CMP-001 Compute & Service Architecture | What major server/VM roles exist and which services live where?
HLD-IDM-001 Identity & Access Architecture | Where identities live, how users/admins authenticate, and how access is controlled.
HLD-SEC-001 Security / Trust-Zone Architecture | Which areas trust which others and where the main security boundaries sit.
HLD-BCK-001 Backup & Recovery Architecture | What protects production systems and how recovery works conceptually.
HLD-OPS-001 Monitoring & Logging Architecture | How systems produce logs/metrics, where they are collected, and how IT sees problems.
HLD-DEP-001 Service Dependency Diagram | What depends on DNS, identity, networking, storage, etc., and therefore what must be built first.