LLD-01-005 — Build Dependencies & Foundation Implementation Order

Project: Project Redstone — Northwind Outdoor Ltd. Design Area: LLD-01 — Physical & Virtual Infrastructure Document Reference: LLD-01-005 Status: Revised — Sprint 2 Design Reconciliation Scope: Northwind v1 Initial Implementation

Design Question

Which components must exist before anything else, and in what order should the initial Northwind infrastructure be established?

1. Decision Summary

Northwind v1 will use a dependency-led implementation sequence rather than attempting to deploy the entire server estate simultaneously.

The revised implementation model recognises that Northwind requires both a functional network security boundary and a controlled administrative foundation before core infrastructure and business services can be commissioned.

The approved conceptual sequence is:

- Physical and Bootstrap Network Foundation.

- HYP01 — Compute Foundation.

- FW01 — Network Security Foundation.

- JUMP01 — Bootstrap Administrative State.

- CORE01 — Core Infrastructure Services.

- OPS01 — Operational Visibility.

- JUMP01 — Operational Administrative State.

- BACKUP01 — Recovery Foundation.

- Foundation Recovery Validation and Readiness Milestone.

- FILE01 — First Business Workload.

The principal design objective is to establish a platform that is:

- Administrable.

- Correctly networked.

- Segmented and access-controlled.

- Observable.

- Auditable.

- Backed up.

- Recoverable.

These capabilities must be established and appropriately validated before Northwind introduces its first significant business-data workload.

This supports the approved recovery-based resilience strategy and prevents business services from being introduced onto an operationally incomplete foundation.

1.1 Relationship to Sprint 2

The revised sequence incorporates the network and security architecture agreed during Sprint 2 planning.

In particular:

- FW01 is explicitly recognised as a foundational infrastructure dependency.

- The Proxmox virtualisation platform must support the approved VLAN architecture.

- JUMP01 must ultimately operate through the approved network security boundary.

- Temporary bootstrap access must not become a permanent alternative administrative route.

- The six approved RHEL virtual machines remain the initial Northwind v1 server estate.

- Foundation services must be operationally validated before FILE01 is accepted into service.

The sequence represents the logical order of dependencies and readiness milestones.

It does not require every implementation task to occur strictly sequentially. Independent activities may proceed in parallel where their prerequisites are satisfied.

2. Dependency Types

Not every implementation dependency represents a hard technical requirement.

Northwind will distinguish between several dependency types.

2.1 Hard Technical Dependency

A component physically or technically cannot operate until another component exists.

For example:

Physical Infrastructure

|

v

HYP01

|

v

Virtual Machines

Northwind virtual machines cannot exist until the virtualisation platform is available.

Similarly, virtual machines requiring connectivity through a particular virtual network must have the necessary virtual networking configured before that connectivity can function.

2.2 Bootstrap Dependency

A temporary mechanism is required to establish the permanent operating model.

For example:

Temporary Controlled Administration

|

v

Build FW01

|

v

Build JUMP01

|

v

Establish Approved Admin Path

|

v

Remove / Restrict Bootstrap Access

The final administrative security model cannot be used to build itself.

Northwind therefore accepts limited temporary administrative access during initial implementation, provided that such access is deliberately controlled and subsequently removed or restricted.

2.3 Network Dependency

A component requires an appropriate network path, routing configuration or security policy before it can communicate with another component.

For example:

Administrative Source

|

v

FW01

|

v

JUMP01

|

v

Management Network

|

v

Infrastructure Servers

The network dependency may involve:

- VLAN configuration.

- Virtual switching.

- Network interface assignment.

- IP addressing.

- Routing.

- Firewall policy.

- DNS resolution.

- Access-control requirements.

Not every network dependency must be satisfied before a virtual machine can be installed.

However, the required connectivity must be established before the relevant service can be commissioned.

2.4 Operational Dependency

A system could technically be deployed without another service, but doing so would prevent it from operating according to the intended Northwind standard.

Examples include:

- DNS.

- Time synchronisation.

- Centralised logging.

- Monitoring.

- Approved administrative access.

A server can technically operate without these capabilities, but Northwind intends subsequent operational systems to use them from the beginning.

2.5 Service-Readiness Dependency

A technical service may function but should not yet be accepted into operational use.

For example:

FILE01 operational ≠ FILE01 ready for business use

Before a business service is accepted into service, supporting operational capabilities such as monitoring, logging, backup and recovery should be established and validated.

3. Stage 0 — Physical and Bootstrap Network Foundation

Before the Northwind virtual server estate can be established, sufficient physical and network connectivity must exist to install and administer the compute platform.

The initial bootstrap environment must provide the minimum connectivity necessary for:

- Physical HYP01 connectivity.

- Initial HYP01 addressing.

- Administrative access.

- Proxmox VE installation and management.

- Initial virtual networking.

- Deployment of FW01.

- Subsequent VLAN and security-zone configuration.

This does not require the entire production network architecture to exist before HYP01 is installed.

Instead, sufficient bootstrap connectivity will be established to allow the remaining network architecture to be progressively implemented.

3.1 Bootstrap Network Requirements

The bootstrap network must provide a controlled method for accessing HYP01 during installation and initial configuration.

This may involve temporary direct or local administrative connectivity while the approved Northwind network security boundary is being established.

Any temporary network configuration must be:

- Deliberately configured.

- Limited to the minimum required.

- Documented.

- Restricted to authorised administration.

- Removed, restricted or replaced when the approved operational network is available.

3.2 Relationship to Network Segmentation

The Northwind v1 design includes four VLANs.

The implementation must establish the required physical and virtual networking to support the approved segmentation architecture.

However, VLAN configuration may be introduced progressively.

The critical requirement is that temporary bootstrap arrangements do not remain in place as uncontrolled paths between security zones.

The detailed VLAN allocation, addressing and interface configuration remain governed by LLD-01-002 and the relevant network implementation documentation.

3.3 Stage Completion Criteria

Stage 0 is complete when:

- Required physical connectivity is available.

- HYP01 can be installed and administered.

- Initial network configuration is documented.

- The network path required for initial virtual machine deployment is available.

- Temporary bootstrap access is identified and controlled.

4. Stage 1 — HYP01: Compute Foundation

HYP01 must be established before the Northwind virtual machine estate can be created.

4.1 Purpose

HYP01 provides:

- Virtual compute.

- Virtual memory.

- Virtual storage.

- Virtual machine lifecycle management.

- Virtual networking integration.

- Console access.

- The platform required by all Northwind virtual servers.

HYP01 will run Proxmox VE, consistent with the approved Northwind physical and virtual infrastructure design.

4.2 Dependency

Physical Infrastructure

|

v

Bootstrap Networking

|

v

HYP01

|

v

Northwind VM Estate

HYP01 represents a hard technical dependency for the virtual infrastructure.

4.3 Initial Configuration Requirements

The initial HYP01 build must establish sufficient compute, storage and networking capabilities to support subsequent virtual machine deployment.

This includes:

- Proxmox VE installation.

- Approved management connectivity.

- Initial host configuration.

- Required virtual networking.

- Appropriate storage configuration.

- Administrative access.

- Basic host validation.

The approved NVMe1/NVMe2 storage placement design must be respected during implementation.

Detailed storage allocation, virtual machine sizing and network interface configuration remain governed by their respective LLD documents.

4.4 Virtual Networking Considerations

HYP01 must provide the virtual networking capabilities required to support FW01 and the other Northwind virtual machines.

The design must account for:

- The approved VLAN architecture.

- Virtual bridge configuration.

- VLAN tagging where applicable.

- FW01 network interfaces.

- Connectivity between the virtualisation platform and the physical network.

- Management access to HYP01.

Proxmox virtual switching and FW01 routing/firewall responsibilities must remain clearly separated.

4.5 Stage Completion Criteria

Stage 1 is complete when:

- HYP01 is operational.

- Proxmox VE management access is validated.

- Initial storage is available.

- Required virtual networking is configured.

- Virtual machine creation and console access are validated.

- The configuration is documented.

5. Stage 2 — FW01: Network Security Foundation

FW01 will be one of the first virtual machines deployed.

Its purpose is to provide the approved routing and firewall boundary for the Northwind v1 environment.

FW01 will run RHEL 10, consistent with the approved Linux server operating-system baseline.

5.1 Purpose

FW01 will provide the network security foundation required to support the approved Northwind segmentation architecture.

Its responsibilities include:

- Routing between applicable Northwind VLANs.

- Enforcing inter-zone firewall policy.

- Controlling permitted infrastructure communication.

- Supporting approved administrative connectivity.

- Providing the required network boundary between security zones.

Additional network services will only be implemented on FW01 where explicitly approved through the relevant detailed design.

5.2 Dependencies

FW01 requires:

- HYP01 operational.

- Required virtual networking available.

- Appropriate virtual network interfaces.

- Approved network addressing.

- Sufficient connectivity for initial administration.

The initial FW01 configuration may be established using controlled bootstrap access before the final administrative model is available.

5.3 Progressive Configuration

FW01 does not need its complete production firewall policy before the next virtual machine can be created.

Instead, its configuration will progress through controlled stages.

Initial State

- RHEL 10 installed.

- Required network interfaces configured.

- Basic routing functionality established.

- Initial security policy applied.

- Administrative connectivity validated.

Operational State

- Approved VLAN routing established.

- Inter-zone firewall policy implemented.

- Administrative access restrictions applied.

- Logging and monitoring integrated.

- Final network connectivity validated.

- Temporary bootstrap access removed or restricted.

The final operational state may depend on services introduced later in the build sequence.

5.4 Security Considerations

Because FW01 provides a security boundary, configuration errors may expose infrastructure services or interrupt network connectivity.

Implementation must therefore include:

- Documented interface assignments.

- Explicit firewall rules.

- Controlled administrative access.

- Configuration validation.

- Testing of permitted communication.

- Testing of prohibited communication.

- Recovery or rollback procedures.

The firewall configuration should follow a least-privilege approach.

Communication between security zones should be permitted only where required by approved Northwind services.

5.5 Stage Completion Criteria

Stage 2 is complete for the initial foundation build when:

- FW01 is deployed.

- Required interfaces are operational.

- Initial routing is validated.

- Necessary administrative connectivity is available.

- Baseline firewall policy is applied.

- The configuration is documented.

Final FW01 operational acceptance will occur after supporting services and the approved security policies have been fully implemented and validated.

6. Stage 3 — JUMP01: Bootstrap Administrative State

JUMP01 will be deployed after the initial compute and network security foundations exist.

Its intended long-term purpose is to provide the controlled administrative entry point into Northwind infrastructure.

However, the complete administrative model cannot exist immediately because several supporting services have not yet been established.

These include:

- Northwind DNS.

- Northwind time synchronisation.

- Centralised logging.

- Monitoring.

- Final firewall policy.

- Final administrative security controls.

JUMP01 will therefore initially operate in a controlled bootstrap state.

6.1 Bootstrap Administration

During this stage, limited temporary administrative access will be permitted where necessary to establish the environment.

Such access must be:

- Deliberately configured.

- Limited to the minimum required.

- Documented.

- Treated as temporary.

- Removed or restricted when the production administrative path becomes available.

The bootstrap mechanism must not silently become a permanent alternative administrative route.

6.2 Relationship to FW01

JUMP01 must be designed to operate through the approved Northwind network security boundary.

During bootstrap, temporary connectivity may be required to complete configuration.

However, the intended operational model must remain:

Approved Administrative Source

|

v

FW01

|

v

JUMP01

|

v

Management Network

|

v

Northwind Infrastructure

The final administrative access model must be validated before JUMP01 is accepted into its operational state.

6.3 Stage Completion Criteria

The bootstrap stage is complete when:

- JUMP01 is deployed.

- Initial administrative access is available.

- Required network connectivity is validated.

- Temporary access mechanisms are documented.

- JUMP01 can support the continued deployment of foundation services.

7. Stage 4 — CORE01: Core Infrastructure Services

CORE01 will be deployed after the initial compute, network security and administrative foundations exist.

CORE01 will provide:

- DNS.

- DHCP.

- NTP/time synchronisation.

These services support consistent operation of the remaining Northwind infrastructure.

7.1 Stable Addressing

CORE01 will use stable/static addressing.

The server cannot depend upon the DHCP service that it is itself responsible for providing.

Other critical infrastructure servers are also expected to use stable addressing according to the final addressing design.

7.2 DNS

Establishing DNS early allows subsequent systems to be configured using Northwind's intended naming architecture rather than relying on temporary addressing or local hostname mappings.

DNS configuration must reflect the approved Northwind network architecture.

Required DNS communication between VLANs must be permitted through the relevant FW01 security policy.

7.3 NTP

Early time synchronisation provides consistent system time across subsequent infrastructure.

This is particularly important for:

- Logs.

- Troubleshooting.

- Security events.

- Authentication.

- Monitoring.

- Scheduled operations.

- Incident investigation.

CORE01 will provide the approved internal time synchronisation service.

Its upstream time sources and configuration will be governed by the relevant detailed design.

7.4 DHCP

CORE01 will provide DHCP services for applicable client/peripheral networks.

Where clients reside in different VLANs, DHCP relay will be required on the relevant Layer-3 gateway.

In the revised Northwind architecture, FW01 is the planned routing boundary and must therefore be considered when designing DHCP relay requirements.

DHCP is not required to bootstrap CORE01 itself.

7.5 Stage Completion Criteria

Stage 4 is complete when:

- CORE01 is operational.

- DNS resolution is validated.

- Time synchronisation is operational.

- DHCP is validated where required.

- Required FW01 communication policies are established.

- Core infrastructure services are documented.

8. Stage 5 — OPS01: Operational Visibility

OPS01 will be established before additional business workloads are introduced.

OPS01 will provide the initial:

- Centralised logging.

- Monitoring.

- Alerting.

- Operational visibility.

8.1 Rationale

Northwind should not build the majority of its infrastructure first and attempt to retrofit observability afterwards.

Instead, the operational model will be established early so subsequent systems can be integrated into monitoring and logging as they are commissioned.

8.2 Infrastructure Integration

The initial infrastructure should progressively be enrolled into OPS01, including where technically appropriate:

- HYP01.

- FW01.

- JUMP01.

- CORE01.

- Later BACKUP01.

- Later FILE01.

This establishes an operational pattern that can be reused throughout subsequent implementation sprints.

8.3 Network Dependencies

OPS01 must be able to communicate with monitored systems using the required protocols and network paths.

Where monitoring or logging traffic crosses security zones, the required communication must be explicitly permitted by FW01.

Monitoring requirements must not result in unrestricted connectivity between VLANs.

8.4 Stage Completion Criteria

Stage 5 is complete when:

- OPS01 is operational.

- Initial centralised logging is available.

- Monitoring is operational.

- Basic alerting is established.

- Existing foundation systems are integrated where applicable.

- Required network communication is validated.

- Operational procedures are documented.

9. Stage 6 — JUMP01: Operational Administrative State

Once CORE01 and OPS01 are available, JUMP01 can transition from its bootstrap state into its intended operational role.

The transition must also include validation of the FW01 network security boundary and the approved administrative access paths.

9.1 Operational Configuration

The final JUMP01 configuration should include, as applicable:

- Northwind DNS integration.

- Time synchronisation.

- Centralised logging.

- Monitoring.

- Hardened SSH configuration.

- Appropriate host security controls.

- Approved administrative users and groups.

- Firewall policy.

- Administrative activity auditing.

- Restricted network access.

9.2 Approved Administrative Path

The intended administrative path is:

Approved Administrative Source

|

v

FW01

|

v

JUMP01

|

v

Management Zone

|

v

Northwind Infrastructure

The exact interfaces, VLANs, routing paths and firewall rules are governed by the approved network design.

The intended security model requires administrators to use JUMP01 as the controlled entry point for routine remote infrastructure administration.

Direct administrative access that bypasses JUMP01 must not remain available as an undocumented alternative.

9.3 Bootstrap Access Removal

Following successful validation, temporary bootstrap administrative paths must be removed or restricted.

This includes reviewing:

- Temporary firewall rules.

- Direct SSH access.

- Temporary network routes.

- Temporary administrative accounts.

- Temporary Proxmox management access arrangements.

- Any temporary access mechanisms introduced during installation.

Any retained emergency access mechanism must be explicitly documented, restricted and approved.

This represents the transition from installation access to operational administrative access.

9.4 FW01 Operational Validation

Before the administrative model is accepted, FW01 must be validated against the approved network security requirements.

Validation should demonstrate that:

- Approved administrative traffic is permitted.

- Unauthorised administrative traffic is blocked.

- Required inter-VLAN communication functions correctly.

- Infrastructure services remain reachable through approved paths.

- Firewall policy does not permit unnecessary access between security zones.

- Network and firewall configuration is documented.

9.5 Stage Completion Criteria

Stage 6 is complete when:

- JUMP01 is operational.

- The approved administrative path is validated.

- FW01 security policy is implemented for the required foundation services.

- JUMP01 logging and monitoring are operational.

- Administrative activity auditing is configured.

- Temporary bootstrap access is removed or restricted.

- Administrative access procedures are documented.

10. Stage 7 — BACKUP01: Recovery Foundation

BACKUP01 will be established before Northwind introduces its first significant business-data workload.

The purpose of this stage is to ensure the infrastructure foundation is recoverable before additional business dependency is placed upon it.

10.1 Initial Backup Coverage

Initial backup coverage should include applicable configuration and data from:

- HYP01.

- FW01.

- JUMP01.

- CORE01.

- OPS01.

The precise backup mechanisms, retention policies and repository architecture will be defined in the dedicated Backup & Recovery LLD.

At this stage, the objective is to establish sufficient recovery capability for the foundation infrastructure.

10.2 Recovery-Based Resilience

Northwind v1 adopts a recovery-based resilience model rather than implementing unnecessary high-availability infrastructure.

The initial environment therefore accepts single instances of core services, provided that appropriate recovery mechanisms are established.

This requires:

- Documented system configurations.

- Appropriate backups.

- Defined restoration procedures.

- Recovery validation.

- Operational documentation.

- Clear recovery responsibilities.

BACKUP01 forms a central component of this strategy.

However, backup availability alone does not guarantee that the environment is recoverable.

10.3 Backup Dependencies

BACKUP01 requires:

- HYP01 operational.

- Required network connectivity.

- Appropriate storage availability.

- Administrative access.

- DNS and time synchronisation where applicable.

- Monitoring and logging integration.

- Required firewall permissions.

The backup design must account for the approved NVMe1/NVMe2 storage architecture.

The existence of separate virtual disks or storage locations on the same physical host must not automatically be interpreted as protection against complete physical host failure.

Protection against physical host loss, storage failure and site-level incidents must be addressed through the approved backup and recovery strategy.

10.4 Stage Completion Criteria

Stage 7 is complete when:

- BACKUP01 is operational.

- Initial backup storage is configured.

- Foundation backup jobs are established.

- Backup execution is validated.

- Backup failures can be detected.

- BACKUP01 is integrated into monitoring and logging.

- Backup procedures are documented.

Formal recovery validation follows in the next stage.

11. Stage 8 — Foundation Recovery Validation

Successful backup completion alone is not sufficient evidence of recoverability.

Northwind must perform appropriate restoration testing.

The principle is:

A backup is not considered operationally proven until Northwind has demonstrated that required information or configuration can be successfully restored.

11.1 Recovery Testing

Recovery testing should validate that:

- Backups are accessible.

- Expected data and configuration are present.

- Restoration procedures are understood.

- Restoration can be performed using documented procedures.

- Restored information is usable.

- Required services can be recovered to an appropriate operational state.

Testing should include representative recovery scenarios appropriate to the foundation infrastructure.

11.2 Recovery Dependencies

The recovery design must account for dependencies between infrastructure components.

For example, restoring CORE01 may be necessary to recover internal DNS and time synchronisation.

However, the recovery procedure must not depend entirely on DNS or other services hosted by CORE01 already being available.

Similarly, recovery procedures for FW01 and JUMP01 must account for the possibility that the normal network security or administrative access paths are unavailable.

Northwind must therefore maintain documented recovery methods that can operate under appropriate degraded infrastructure conditions.

11.3 Recovery Evidence

Evidence should be retained for the implementation record and future operational documentation.

This should include:

- Recovery test objective.

- System or configuration restored.

- Backup source.

- Restoration procedure followed.

- Test result.

- Issues encountered.

- Corrective actions.

- Relevant recovery timing observations.

Recovery testing should provide practical evidence rather than relying solely on successful backup job reports.

12. Stage 9 — Foundation Recovery and Readiness Milestone

Before introducing the first significant business workload, Northwind will complete a formal foundation readiness milestone.

At this point, the environment should demonstrate the following capabilities.

12.1 Compute

- HYP01 operational.

- Proxmox VE management validated.

- Virtual machine hosting validated.

- Approved storage configuration established.

12.2 Networking and Security

- FW01 operational.

- Required VLAN routing established.

- Approved inter-zone firewall policy implemented.

- Required infrastructure communication validated.

- Unauthorised communication appropriately restricted.

12.3 Administration

- JUMP01 operational.

- Approved administrative path validated.

- Temporary bootstrap access removed or restricted.

- Administrative access procedures documented.

12.4 Core Services

- DNS operational.

- DHCP operational where required.

- NTP/time synchronisation operational.

- Required infrastructure service communication validated.

12.5 Operations

- Centralised logging operational.

- Monitoring operational.

- Alerting capability established.

- Foundation systems integrated into operational visibility.

12.6 Recovery

- BACKUP01 operational.

- Foundation infrastructure protected.

- Restoration procedures tested.

- Recovery evidence retained.

- Relevant recovery documentation completed.

12.7 Foundation Milestone

The milestone can be represented as:

+--------------------------------------+

|      NORTHWIND FOUNDATION READY      |

+--------------------------------------+

|                                      |

|  [✓] Compute operational             |

|  [✓] Network segmentation established|

|  [✓] Firewall policy validated       |

|  [✓] Administration controlled       |

|  [✓] Core services operational       |

|  [✓] Logging established             |

|  [✓] Monitoring established          |

|  [✓] Backups operational             |

|  [✓] Recovery tested                 |

|                                      |

+------------------+-------------------+

|

v

Business Workloads

Passing this milestone indicates that Northwind has an operational infrastructure foundation suitable for the controlled introduction of business services.

The milestone must be supported by appropriate technical validation and implementation evidence.

13. Stage 10 — FILE01: First Business Workload

FILE01 will become the first major business-data workload introduced after the foundation milestone.

This sequencing ensures that FILE01 is deployed into an environment where supporting operational capabilities already exist.

13.1 Deployment Sequence

FILE01 can therefore be commissioned through the established Northwind infrastructure model:

Deploy RHEL 10 Virtual Machine

|

v

Apply Server Baseline

|

v

Configure Network / DNS / Time

|

v

Apply Security Controls

|

v

Configure Administrative Access

|

v

Enable Central Logging

|

v

Enable Monitoring

|

v

Configure Backup

|

v

Test Recovery

|

v

Validate File Service

|

v

Accept into Service

13.2 Network and Security Integration

FILE01 must be connected to the appropriate Northwind network segment.

Its network connectivity must follow the approved VLAN architecture and FW01 security policy.

Access to file services must be restricted to authorised users, systems and network paths.

The detailed file-service access model will be governed by the relevant File Services LLD.

13.3 Backup Integration

BACKUP01 will be updated to protect FILE01 configuration and business data according to the later File Services and Backup & Recovery designs.

Backup coverage must be established before FILE01 is accepted for operational business use.

Appropriate recovery testing must demonstrate that protected business information can be restored.

13.4 Stage Completion Criteria

FILE01 is ready for operational acceptance when:

- The approved RHEL server baseline is applied.

- Network connectivity is validated.

- Required security controls are implemented.

- Administrative access is controlled.

- Logging and monitoring are operational.

- Backup protection is established.

- Recovery testing is completed.

- File-service functionality is validated.

- Required documentation is completed.

14. Server Commissioning Principle

LLD-01-005 establishes an operational principle that should apply to future Northwind servers.

A server is not considered complete merely because its primary application or service is functioning.

Before acceptance into operational service, a server should normally be:

- Built according to the approved baseline.

- Securely administered.

- Correctly networked.

- Integrated with DNS.

- Time synchronised.

- Hardened.

- Centrally logged.

- Monitored.

- Backed up where required.

- Recovery tested where appropriate.

- Functionally validated.

- Documented.

14.1 Network Security Validation

Where a server communicates across Northwind security zones, commissioning must also validate:

- Required routing.

- Permitted firewall rules.

- Restricted access.

- Appropriate network segmentation.

- Absence of unnecessary administrative connectivity.

14.2 Documentation Requirements

Commissioning documentation should include:

- Server identity and role.

- Operating-system version.

- Network configuration.

- Storage configuration.

- Installed services.

- Security configuration.

- Monitoring integration.

- Backup configuration.

- Validation results.

- Known issues or exceptions.

This principle should later be formalised into a Northwind Server Commissioning SOP and checklist.

15. Dependency Sequence

The approved conceptual dependency sequence is:

PHYSICAL INFRASTRUCTURE

|

v

BOOTSTRAP NETWORK

|

v

HYP01

Proxmox VE Platform

|

v

FW01

Initial Network Security

|

v

JUMP01

Bootstrap Admin State

|

v

CORE01

DNS / DHCP / NTP

|

v

OPS01

Logging / Monitoring

|

v

JUMP01 OPERATIONAL

+ FW01 Policy Validation

|

v

BACKUP01

Recovery Foundation

|

v

RECOVERY VALIDATION

|

v

+--------------------------------+

|      FOUNDATION MILESTONE      |

|--------------------------------|

| Compute operational            |

| Network segmentation validated |

| Administration controlled      |

| Core services operational      |

| Observable and auditable       |

| Backed up                      |

| Recovery tested                |

+---------------+----------------+

|

v

FILE01

First Business Workload

|

v

Logging / Monitoring / Backup

|

v

BUSINESS SERVICE READY

15.1 Dependency Interpretation

The sequence identifies the preferred order for establishing Northwind's operational capabilities.

It does not imply that every server must be fully configured before the next server can be deployed.

Some activities may overlap.

For example:

- FW01 can be initially deployed before its final monitoring and logging integration.

- JUMP01 can operate in a controlled bootstrap state before CORE01 and OPS01 are available.

- Infrastructure documentation can be developed alongside implementation.

- Backup procedures can be prepared before BACKUP01 is fully operational.

The critical requirement is that dependent capabilities are validated before the relevant operational readiness milestone is accepted.

15.2 Dependency Governance

Implementation planning must distinguish between:

Hard dependencies: Activities that cannot proceed until a prerequisite exists.

Operational dependencies: Activities that may technically proceed but cannot be accepted into operational service until supporting capabilities are available.

Documentation dependencies: Activities requiring an approved design, configuration standard or implementation procedure.

Acceptance dependencies: Activities requiring successful validation before a milestone can be completed.

This distinction will support realistic Sprint 2 planning and prevent unnecessary sequencing constraints.

16. Design Trade-Offs

16.1 Bootstrap Access

Temporary direct administration is accepted during initial implementation because the final bastion architecture cannot exist before FW01, JUMP01 and their supporting services have been established.

Risk is controlled by documenting, restricting and subsequently removing temporary access.

16.2 Early Firewall Deployment

FW01 is deliberately introduced before the remaining infrastructure services.

This establishes the network security foundation early and allows subsequent services to be deployed within the approved segmentation architecture.

However, FW01 must initially operate with a limited configuration because its final operational dependencies are not yet available.

This creates a controlled distinction between initial firewall deployment and final firewall acceptance.

16.3 Early Observability

OPS01 is prioritised before business workloads so that subsequent infrastructure is observable from the beginning rather than monitoring being retrofitted later.

16.4 Recovery Before Business Services

BACKUP01 is deliberately deployed before FILE01.

Although FILE01 could technically be built first, doing so would introduce a business-data workload before the recovery platform was established.

Given Northwind's recovery-based resilience model, recoverability is considered part of the infrastructure foundation.

16.5 Single-Instance Foundation Services

FW01, CORE01, OPS01 and BACKUP01 remain single instances during v1.

This is consistent with the existing decision to prioritise documented recovery over unnecessary high-availability complexity.

The design accepts that failure of a single foundation component may interrupt dependent services.

This risk must be managed through monitoring, documented recovery procedures and appropriate backup protection.

16.6 Dependency-Led Versus Parallel Implementation

A strictly sequential implementation would simplify dependency management but could unnecessarily delay independent work.

A completely parallel implementation could create configuration inconsistencies and unresolved service dependencies.

Northwind will therefore use a dependency-led model that permits parallel implementation where appropriate, while retaining formal readiness and acceptance milestones.

17. Implementation Implications

This dependency model should directly inform:

- Sprint planning.

- Implementation Statements of Work.

- Change records.

- Build guides.

- Test plans.

- Technical acceptance.

- Backup validation.

- Recovery testing.

- Server commissioning procedures.

17.1 Sprint Planning

The implementation backlog should reflect the dependencies established in this document.

Tasks should be organised around the capabilities required to establish the Northwind foundation.

In particular, the backlog should distinguish between:

- Bootstrap network preparation.

- HYP01 configuration.

- FW01 deployment and validation.

- JUMP01 bootstrap deployment.

- CORE01 service deployment.

- OPS01 operational visibility.

- JUMP01 operational transition.

- BACKUP01 deployment.

- Recovery testing.

- Foundation acceptance.

- FILE01 deployment.

These are logical work packages rather than mandatory individual sprint boundaries.

The actual allocation of work to sprints will depend on task estimation, available capacity and implementation progress.

17.2 Implementation Documentation

Each implementation activity should produce sufficient documentation to support:

- Configuration review.

- Troubleshooting.

- Rebuild and recovery.

- Future maintenance.

- Technical handover.

- Operational consistency.

Documentation should be captured during implementation rather than reconstructed after the work is complete.

17.3 Implementation Records

Completed implementation activities should retain:

- Objective.

- Work performed.

- Commands and configuration changes where applicable.

- Validation evidence.

- Findings and lessons learned.

- Final result.

- Outstanding issues.

- Next implementation activity.

These records will support future recovery, audits and infrastructure changes.

17.4 Stage Acceptance

Each stage should have appropriate acceptance criteria before dependent operational stages proceed.

Where a stage is intentionally accepted in a temporary bootstrap state, the remaining work required for full operational acceptance must be recorded.

This prevents temporary implementation arrangements from being mistaken for completed production configurations.

18. Deferred Detailed Design

This document establishes dependency and implementation order, not the complete technical configuration of each component.

The following remain subject to their respective detailed designs and approved implementation records:

- Detailed physical network configuration.

- VLAN interface assignments.

- IP addressing.

- FW01 interface configuration.

- Routing configuration.

- Firewall rules.

- DHCP scopes.

- DHCP relay configuration.

- DNS architecture.

- NTP configuration.

- Monitoring platform.

- Logging implementation.

- Backup technology.

- Backup retention periods.

- Restore procedures.

- RHEL server baseline configuration.

- Detailed security hardening.

- Storage layouts.

- File-service configuration.

- Detailed server commissioning procedures.

18.1 Previously Approved Design Decisions

Decisions already approved through other Northwind design documents must not be reopened solely because their implementation details are referenced here.

In particular:

- The four-VLAN network architecture remains governed by LLD-01-002.

- The physical and virtual infrastructure architecture remains governed by LLD-01-001.

- The RHEL 10 server baseline remains governed by LLD-01-003.

- The approved NVMe1/NVMe2 storage placement remains applicable.

- The recovery-based resilience strategy remains applicable.

This document defines how these approved design elements are introduced in a controlled dependency sequence.

19. Decision

Accepted for Northwind v1 — Revised during Sprint 2 Design Reconciliation.

Northwind Outdoor Ltd. will establish compute, network security, controlled administration, core infrastructure services, operational visibility and recovery capability before introducing its first significant business-data workload.

The resulting conceptual implementation sequence is:

Bootstrap Network → HYP01 → FW01 → JUMP01 Bootstrap → CORE01 → OPS01 → JUMP01 Operational / FW01 Validation → BACKUP01 → Recovery Validation → Foundation Milestone → FILE01

This sequence provides a controlled transition from an empty physical platform to an administrable, segmented, observable and recoverable infrastructure foundation suitable for subsequent Northwind business services.

The sequence represents logical implementation dependencies and operational acceptance milestones rather than an inflexible requirement to perform every technical activity sequentially.

Temporary bootstrap arrangements are permitted where necessary, provided they are controlled, documented and removed or restricted before the relevant operational acceptance milestone.

The foundation must demonstrate appropriate network security, administrative control, operational visibility, backup protection and recovery capability before FILE01 is accepted for business use.