## Sprint 2
NIM | Title | Parent epic | Priority | Points
1 | Verify HYP01 Platform Readiness | Platform & Virtualisation Foundation | High | 2
2 | Finalise FW01 and JUMP01 VM Specifications | Platform & Virtualisation Foundation | High | 2
3 | Finalise Network Addressing and Interface Schedule | Platform & Virtualisation Foundation | High | 3
4 | Validate and Secure HYP01 Management Access | Platform & Virtualisation Foundation | High | 5
5 | Deploy FW01 RHEL Virtual Machine | Platform & Virtualisation Foundation | High | 5
6 | Configure FW01 Interfaces and VLAN Gateways | Core Infrastructure Services | High | 5
7 | Configure FW01 Routing and NAT | Core Infrastructure Services | High | 5
8 | Implement FW01 Firewall Security Policy | Core Infrastructure Services | High | 8
9 | Configure Interim Network Service Dependencies | Core Infrastructure Services | Medium | 3
10 | Validate FW01 Network Connectivity and Isolation | Core Infrastructure Services | High | 5
11 | Deploy JUMP01 RHEL Virtual Machine | Administrative Access Foundation | High | 5
12 | Configure Administrative Accounts and sudo | Administrative Access Foundation | High | 3
13 | Implement JUMP01 SSH Hardening | Administrative Access Foundation | High | 5
14 | Establish Routed Administrative Access to JUMP01 | Administrative Access Foundation | High | 5
15 | Configure and Validate SSH ProxyJump | Administrative Access Foundation | High | 5
16 | Implement RHEL Security and Operational Baseline | Operational Visibility | High | 5
17 | Establish Secure Operational and Credential Procedures | Administrative Access Foundation | Medium | 3
18 | Implement Configuration Protection and Rollback | Backup & Recovery Foundation | High | 5
19 | Implement Interim Proxmox VM Backups | Backup & Recovery Foundation | High | 8
20 | Validate VM Restoration and Emergency Recovery | Backup & Recovery Foundation | High | 8
21 | Complete Security and Commissioning Acceptance | Operational Visibility | High | 5
22 | Complete Implementation Documentation and Handover | Platform & Virtualisation Foundation | Medium | 5