LLD-01-005 — Build Dependencies & Foundation Implementation Order

Question

Which components must exist before anything else, and in what order should the initial Northwind infrastructure be established?

1. Decision Summary

Northwind v1 will use a dependency-led implementation sequence rather than attempting to deploy the entire server estate simultaneously.

The proposed sequence is:

- Bootstrap Network Foundation

- HYP01 — Compute Foundation

- JUMP01 — Bootstrap State

- CORE01 — Core Infrastructure Services

- OPS01 — Operational Visibility

- JUMP01 — Operational State

- BACKUP01 — Recovery Foundation

- Foundation Recovery Milestone

- FILE01 — First Business Workload

The principal design objective is to establish a platform that is:

- administrable;

- networked;

- observable;

- auditable;

- backed up;

- recoverable;

before Northwind introduces its first business-data workload.

This supports the existing recovery-based resilience strategy and prevents business services from being introduced onto an operationally incomplete foundation.

2. Dependency Types

Not every implementation dependency represents a hard technical requirement.

Northwind will distinguish between several dependency types.

2.1 Hard Technical Dependency

A component physically or technically cannot operate until another component exists.

Example:

HYP01

↓

Virtual Machines

Northwind VMs cannot exist until the virtualisation platform is available.

2.2 Bootstrap Dependency

A temporary mechanism is required to establish the permanent operating model.

Example:

Temporary Controlled Administration

↓

Build JUMP01

↓

Establish Bastion Model

↓

Remove / Restrict Bootstrap Access

The final administrative security model cannot be used to build itself.

2.3 Operational Dependency

A system could technically be deployed without another service, but doing so would prevent it from operating according to the intended Northwind standard.

Examples include:

- DNS;

- time synchronisation;

- centralised logging;

- monitoring.

A server can technically operate without these capabilities, but Northwind intends subsequent production systems to use them from the beginning.

2.4 Service-Readiness Dependency

A technical service may function but should not yet be accepted into operational use.

For example:

FILE01 operational

≠

FILE01 ready for production

Before a business service is accepted into service, supporting operational capabilities such as monitoring, logging, backup and recovery should be established and validated.

3. Stage 0 — Bootstrap Network Foundation

Before the Northwind virtual server estate can be established, sufficient physical and network connectivity must exist to install and administer the compute platform.

The initial bootstrap network must provide the minimum connectivity necessary for:

- physical HYP01 connectivity;

- initial HYP01 addressing;

- gateway connectivity where required;

- administrative access;

- initial virtual networking;

- subsequent VLAN and security-zone configuration.

This does not require the entire production network architecture to exist before HYP01 is installed.

Instead, sufficient bootstrap connectivity will be established to allow the remaining network architecture to be progressively implemented.

Temporary network configuration introduced during bootstrap must be documented and subsequently removed, restricted or replaced by the approved production design.

4. Stage 1 — HYP01: Compute Foundation

HYP01 must be established before the Northwind VM estate can be created.

Purpose

HYP01 provides:

- virtual compute;

- virtual memory;

- virtual storage;

- VM lifecycle management;

- virtual networking integration;

- console access;

- the platform required by all Northwind virtual servers.

Dependency

Physical Infrastructure

↓

Bootstrap Networking

↓

HYP01

↓

Northwind VM Estate

HYP01 therefore represents a hard technical dependency for the virtual infrastructure.

The initial HYP01 build must establish sufficient storage and virtual networking to support subsequent VM deployment.

Detailed service-specific networking remains governed by later design and implementation activities.

5. Stage 2 — JUMP01: Bootstrap State

JUMP01 will be one of the first virtual machines deployed.

Its intended long-term purpose is to provide the controlled administrative entry point into Northwind infrastructure.

However, the complete bastion model cannot exist immediately because several supporting services have not yet been established.

These include:

- Northwind DNS;

- Northwind time synchronisation;

- centralised logging;

- monitoring;

- final firewall policy.

JUMP01 will therefore initially operate in a controlled bootstrap state.

Bootstrap Administration

During this stage, limited temporary administrative access will be permitted where necessary to establish the environment.

Such access must be:

- deliberately configured;

- limited to the minimum required;

- documented;

- treated as temporary;

- removed or restricted when the production administrative path becomes available.

The bootstrap mechanism must not silently become a permanent alternative administrative route.

6. Stage 3 — CORE01: Core Infrastructure Services

CORE01 will be deployed after the initial compute and administrative foundations exist.

CORE01 will provide:

- DNS;

- DHCP;

- NTP/time synchronisation.

Stable Addressing

CORE01 will use stable/static addressing.

The server cannot depend upon the DHCP service that it is itself responsible for providing.

Other critical infrastructure servers are also expected to use stable addressing according to the final addressing design.

DNS

Establishing DNS early allows subsequent systems to be configured using Northwind's intended naming architecture rather than relying on temporary addressing or local hostname mappings.

NTP

Early time synchronisation provides consistent system time across subsequent infrastructure.

This is particularly important for:

- logs;

- troubleshooting;

- security events;

- authentication;

- monitoring;

- scheduled operations;

- incident investigation.

DHCP

CORE01 will provide DHCP services for applicable client/peripheral networks.

Where clients reside in different VLANs, DHCP relay will be required on the relevant Layer-3 gateway.

DHCP is not required to bootstrap CORE01 itself.

7. Stage 4 — OPS01: Operational Visibility

OPS01 will be established before additional business workloads are introduced.

OPS01 will provide the initial:

- centralised logging;

- monitoring;

- alerting;

- operational visibility.

Rationale

Northwind should not build the majority of its infrastructure first and attempt to retrofit observability afterwards.

Instead, the operational model will be established early so subsequent systems can be integrated into monitoring and logging as they are commissioned.

The initial infrastructure should therefore progressively be enrolled into OPS01, including where technically appropriate:

- HYP01;

- JUMP01;

- CORE01;

- later BACKUP01;

- later FILE01.

This establishes an operational pattern that can be reused throughout subsequent implementation sprints.

8. Stage 5 — JUMP01: Operational State

Once CORE01 and OPS01 are available, JUMP01 can transition from its bootstrap state into its intended operational role.

The final configuration should include, as applicable:

- Northwind DNS integration;

- time synchronisation;

- centralised logging;

- monitoring;

- hardened SSH configuration;

- appropriate host security controls;

- approved administrative users/groups;

- firewall policy;

- administrative activity auditing;

- restricted network access.

The intended administrative path can then become:

Administrator

↓

USER / Approved Admin Source

↓

Firewall / Security Policy

↓

JUMP01

↓

Management Zone

↓

Northwind Infrastructure

Following successful validation, temporary bootstrap administrative paths must be removed or restricted.

This represents the transition from:

installation access

to:

operational administrative access.

9. Stage 6 — BACKUP01: Recovery Foundation

BACKUP01 will be established before Northwind introduces its first significant business-data workload.

The purpose of this stage is to ensure the infrastructure foundation is recoverable before additional business dependency is placed upon it.

Initial backup coverage should include applicable configuration/data from:

- HYP01;

- JUMP01;

- CORE01;

- OPS01.

The precise backup mechanisms, retention policies and repository architecture will be defined in the dedicated Backup & Recovery LLD.

At this stage, the objective is to establish sufficient recovery capability for the foundation infrastructure.

10. Recovery Validation

Successful backup completion alone is not sufficient evidence of recoverability.

Northwind must perform appropriate restoration testing.

The principle is:

A backup is not considered operationally proven until Northwind has demonstrated that required information or configuration can be successfully restored.

Recovery testing should validate that:

- backups are accessible;

- expected data/configuration is present;

- restoration procedures are understood;

- restoration can be performed using documented procedures;

- restored information is usable.

Evidence should be retained for the implementation record and future operational documentation.

11. Stage 7 — Foundation Recovery Milestone

Before introducing the first significant business workload, Northwind will complete a formal foundation milestone.

At this point, the environment should demonstrate:

Compute

- HYP01 operational;

- VM hosting validated.

Administration

- JUMP01 operational;

- approved administrative path validated;

- temporary bootstrap access removed/restricted.

Core Services

- DNS operational;

- DHCP operational where required;

- NTP/time synchronisation operational.

Operations

- centralised logging operational;

- monitoring operational;

- alerting capability established.

Recovery

- BACKUP01 operational;

- foundation infrastructure protected;

- restoration procedure tested;

- recovery evidence retained.

The milestone can therefore be represented as:

┌──────────────────────────────┐

│ NORTHWIND FOUNDATION READY   │

│                              │

│ ✓ Compute operational        │

│ ✓ Administration controlled  │

│ ✓ Core services operational  │

│ ✓ Logging established        │

│ ✓ Monitoring established     │

│ ✓ Backups operational        │

│ ✓ Recovery tested            │

└──────────────┬───────────────┘

↓

Business Workloads

Passing this milestone indicates that Northwind has an operational infrastructure foundation suitable for the controlled introduction of business services.

12. Stage 8 — FILE01: First Business Workload

FILE01 will become the first major business-data workload introduced after the foundation milestone.

This sequencing ensures that FILE01 is deployed into an environment where supporting operational capabilities already exist.

FILE01 can therefore be commissioned through the established Northwind infrastructure model:

Deploy

↓

Apply Server Baseline

↓

Configure Network / DNS / Time

↓

Apply Security Controls

↓

Configure Administrative Access

↓

Enable Logging

↓

Enable Monitoring

↓

Configure Backup

↓

Test Recovery

↓

Validate File Service

↓

Accept into Service

BACKUP01 will be updated to protect FILE01 configuration and business data according to the later File Services and Backup & Recovery designs.

13. Server Commissioning Principle

LLD-01-005 establishes an operational principle that should apply to future Northwind servers.

A server is not considered complete merely because its primary application or service is functioning.

Before acceptance into operational service, a server should normally be:

- built according to the approved baseline;

- securely administered;

- correctly networked;

- integrated with DNS;

- time synchronised;

- hardened;

- centrally logged;

- monitored;

- backed up where required;

- recovery tested where appropriate;

- functionally validated;

- documented.

This principle should later be formalised into a Northwind Server Commissioning SOP / Checklist.

14. Dependency Sequence

The approved conceptual dependency sequence is:

Bootstrap Network Foundation

↓

HYP01

↓

JUMP01 Bootstrap

↓

CORE01

DNS / DHCP / NTP

↓

OPS01

Logging / Monitoring

↓

JUMP01 Operational

↓

BACKUP01

↓

Recovery Validation

↓

┌─────────────────────────┐

│ FOUNDATION MILESTONE    │

│                         │

│ Administered            │

│ Observable              │

│ Auditable               │

│ Backed Up               │

│ Recovery Tested         │

└────────────┬────────────┘

↓

FILE01

↓

Logging / Monitoring / Backup

↓

Business Service Ready

15. Design Trade-Offs

Bootstrap Access

Temporary direct administration is accepted during initial implementation because the final bastion architecture cannot exist before JUMP01 and its supporting services have been established.

Risk is controlled by documenting, restricting and subsequently removing temporary access.

Early Observability

OPS01 is prioritised before business workloads so that subsequent infrastructure is observable from the beginning rather than monitoring being retrofitted later.

Recovery Before Business Services

BACKUP01 is deliberately deployed before FILE01.

Although FILE01 could technically be built first, doing so would introduce a business-data workload before the recovery platform was established.

Given Northwind's recovery-based resilience model, recoverability is considered part of the infrastructure foundation.

Single-Instance Foundation Services

CORE01, OPS01 and BACKUP01 remain single instances during v1.

This is consistent with the existing decision to prioritise documented recovery over unnecessary high-availability complexity.

16. Implementation Implications

This dependency model should directly inform:

- Sprint planning;

- implementation SOWs;

- change records;

- build guides;

- test plans;

- UAT/technical acceptance;

- backup validation;

- recovery testing;

- server commissioning procedures.

Implementation should follow dependency order rather than attempting to create all VMs immediately.

Each stage should have appropriate acceptance criteria before dependent stages proceed.

17. Deferred Detailed Design

This document establishes dependency and implementation order, not the complete technical configuration of each component.

The following remain subject to subsequent detailed design:

- exact VLAN IDs;

- IP addressing;

- firewall rules;

- DHCP scopes;

- DHCP relay configuration;

- DNS architecture;

- NTP configuration;

- monitoring platform;

- logging implementation;

- backup technology;

- retention periods;

- restore procedures;

- RHEL server baseline configuration;

- detailed hardening;

- storage layouts;

- file-service configuration.

These decisions will be addressed through the relevant later LLDs and implementation work.

18. Decision

Accepted as the proposed Northwind v1 foundation build dependency model.

Northwind will establish compute, controlled administration, core infrastructure services, operational visibility and recovery capability before introducing its first significant business-data workload.

The resulting implementation sequence is:

Bootstrap Network → HYP01 → JUMP01 Bootstrap → CORE01 → OPS01 → JUMP01 Operational → BACKUP01 → Recovery Validation → Foundation Milestone → FILE01

This sequence provides a controlled transition from an empty physical platform to an administrable, observable and recoverable infrastructure foundation suitable for subsequent Northwind business services.