## Summary
Northwind Outdoor Ltd. ¦ RTM Summary
Formula-driven baseline overview from the RTM register. Counts update as the register is maintained.
Baseline overview | Value | Control / interpretation | BRD source
Total requirements | 56 | Functional and non-functional requirements in baseline | BRD v1.0 §§8–9
Functional requirements | 38 | BR-001 to BR-038 | BRD v1.0 §8
Non-functional requirements | 18 | NFR-001 to NFR-018 | BRD v1.0 §9
Baseline lifecycle status | Baseline Pending Approval | Current BRD v1.0 baseline state | BRD v1.0 Baseline
Counts by Type | Count |  | Counts by Priority | Count | Counts by Business Driver | Count
Functional | 38 |  | Must | 40 | BD-001 | 23
Non-Functional | 18 |  | Should | 15 | BD-002 | 27
|  |  | Could | 1 | BD-003 | 6
Counts by Lifecycle Status | Count
Baseline Pending Approval | 56

## RTM
Northwind Outdoor Ltd. ¦ Requirements Traceability Matrix
Source baseline: BRD v1.0 (10-Aug-2026). Later lifecycle fields intentionally remain TBD until formally defined.
RHCSA Objective | Requirement ID | Type | Requirement / Title | Priority | Business Owner | DF | BD | CAP (Primary) | CAP (Secondary) | BRD | Primary AD | Key ADs | Secondary Ads | HLD (Primary) | HLD (Secondary) | LLD (Primary) | LLD (Secondary) | ADR | SOW | Sprint | Test / UAT | Acceptance Criteria | Status | Owner | Notes
Not Yet Defined | BR-001 | Functional | Business Service Continuity — The proposed solution shall maintain existing business-critical services throughout implementation and provide capabilities that improve security, resilience, operational efficiency and scalability. | Must | Operations Director | TBD | BD-002 | - |  | BRD v1.0 BR-001 | AD-12 | AD-07, AD-06, AD-09 | AD-01, AD-08, AD-10 | DD-012 — Availability & Resilience Strategy |  | Not Yet Defined |  | Not Yet Defined |  |  | Not Yet Defined | Existing business-critical services remain available following implementation. | Baseline Pending Approval | TBD – delivery owner not assigned | BRD note: Foundation requirement. ¦ DF: No formal Discovery Finding IDs are defined in the BRD. CAP: No formal capability catalogue/IDs are defined in the BRD.
Not Yet Defined | BR-002 | Functional | Centralised User Identity Management — The organisation requires centrally managed capabilities for creating, modifying and removing user accounts and associated access. | Must | IT Manager | TBD | BD-001 | CAP-001 |  | BRD v1.0 BR-002 | AD-03 | AD-04,AD-08,AD-09,AD-10 | AD-01, AD-02,AD-05 | DD-002 — Identity & Access Management Architecture |  | Not Yet Defined |  | Not Yet Defined |  |  | Not Yet Defined | User accounts can be managed through a controlled central process. | Baseline Pending Approval | TBD – delivery owner not assigned | BRD note: Foundation capability. ¦ DF: No formal Discovery Finding IDs are defined in the BRD. CAP: No formal capability catalogue/IDs are defined in the BRD.
Not Yet Defined | BR-003 | Functional | User Lifecycle Management — The organisation shall have a documented and controlled process for managing employee joiners, movers and leavers, with clearly defined responsibilities between HR and IT. | Must | HR Manager | TBD | BD-001 | CAP-001 |  | BRD v1.0 BR-003 | AD-10 | AD-03, AD-05, AD-08, | AD-11, AD-02, AD-09 | DD-002 — Identity & Access Management Architecture |  | Not Yet Defined |  | Not Yet Defined |  |  | Not Yet Defined | Joiner, mover and leaver activities follow an agreed and documented process. | Baseline Pending Approval | TBD – delivery owner not assigned | BRD note: Builds on existing provisioning requirement and Workshop 2 decision. ¦ DF: No formal Discovery Finding IDs are defined in the BRD. CAP: No formal capability catalogue/IDs are defined in the BRD.
Not Yet Defined | BR-004 | Functional | User Provisioning Automation — The solution should reduce manual administration by automating appropriate user onboarding, role changes and offboarding activities where practical. | Must | HR Manager | TBD | BD-001 | CAP-002 | CAP-001 | BRD v1.0 BR-004 | AD-10 | AD-03, AD-05, AD-08 | AD-11, AD-02, AD-09 | DD-002 — Identity & Access Management Architecture |  | Not Yet Defined |  | Not Yet Defined |  |  | Not Yet Defined | Agreed user lifecycle activities can be completed through defined automated workflows where appropriate. | Baseline Pending Approval | TBD – delivery owner not assigned | BRD note: Automation approach to be determined during design. ¦ DF: No formal Discovery Finding IDs are defined in the BRD. CAP: No formal capability catalogue/IDs are defined in the BRD.
Not Yet Defined | BR-005 | Functional | Role-Based Access Control — User access shall be assigned according to business role and departmental responsibilities. | Must | IT Manager | TBD | BD-002 | CAP-001 |  | BRD v1.0 BR-005 | AD-03 | AD-08, AD-05, AD-10 | AD-02, AD-11, AD-09 | DD-002 — Identity & Access Management Architecture |  | Not Yet Defined |  | Not Yet Defined |  |  | Not Yet Defined | Users can access only resources authorised for their role. | Baseline Pending Approval | TBD – delivery owner not assigned | BRD note: Supports least privilege. ¦ DF: No formal Discovery Finding IDs are defined in the BRD. CAP: No formal capability catalogue/IDs are defined in the BRD.
Not Yet Defined | BR-006 | Functional | Secure File Services — The organisation requires secure, centrally managed file storage for departmental and shared business information. | Must | Operations Manager | TBD | BD-001 | CAP-003 | CAP-017 | BRD v1.0 BR-006 | AD-05 | AD-06, AD-03, AD-08, AD-07 | AD-01, AD-09, AD-10, AD-12, AD-02 | DD-003 — File & Data Services Architecture | DD-004 — Storage Architecture | Not Yet Defined |  | Not Yet Defined |  |  | Not Yet Defined | Departments can securely access authorised shared files. | Baseline Pending Approval | TBD – delivery owner not assigned | BRD note: Business-critical capability. ¦ DF: No formal Discovery Finding IDs are defined in the BRD. CAP: No formal capability catalogue/IDs are defined in the BRD.
Not Yet Defined | BR-007 | Functional | Structured Data Organisation — The solution shall support consistent organisation of business information, including standard folder structures, naming conventions and governance processes. | Should | Operations Manager | TBD | BD-001 | CAP-003 |  | BRD v1.0 BR-007 | AD-05 | AD-10, AD-03, AD-08 | AD-06, AD-09, AD-07 | DD-003 — File & Data Services Architecture | DD-004 — Storage Architecture | Not Yet Defined |  | Not Yet Defined |  |  | Not Yet Defined | Business data follows agreed organisational standards. | Baseline Pending Approval | TBD – delivery owner not assigned | BRD note: Detailed implementation defined during design. ¦ DF: No formal Discovery Finding IDs are defined in the BRD. CAP: No formal capability catalogue/IDs are defined in the BRD.
Not Yet Defined | BR-008 | Functional | Departmental Data Segregation — Departmental information shall be logically separated to prevent unauthorised access. | Must | Finance Manager | TBD | BD-002 | CAP-003 | CAP-001 | BRD v1.0 BR-008 | AD-08 | AD-10, AD-05, AD-03 | AD-06, AD-09, AD-07 | DD-003 — File & Data Services Architecture | DD-009 Network Security & Segmentation | Not Yet Defined |  | Not Yet Defined |  |  | Not Yet Defined | Users cannot access data outside their authorised departments. | Baseline Pending Approval | TBD – delivery owner not assigned | BRD note: Supports confidentiality. ¦ DF: No formal Discovery Finding IDs are defined in the BRD. CAP: No formal capability catalogue/IDs are defined in the BRD.
Not Yet Defined | BR-009 | Functional | Secure Data Access — Access to business data shall be authenticated, authorised and auditable. | Must | IT Manager | TBD | BD-002 | CAP-001 | CAP-017 CAP-005 | BRD v1.0 BR-009 | AD-08 | AD-03, AD-09, AD-05 | AD-10, AD-06, AD-11, AD-02 | DD-003 — File & Data Services Architecture | DD-002 Identity & Access Management DD-007 Logging & Audit | Not Yet Defined |  | Not Yet Defined |  |  | Not Yet Defined | Only authorised users can access sensitive business data and access can be appropriately audited. | Baseline Pending Approval | TBD – delivery owner not assigned | BRD note: Security requirement. ¦ DF: No formal Discovery Finding IDs are defined in the BRD. CAP: No formal capability catalogue/IDs are defined in the BRD.
Not Yet Defined | BR-010 | Functional | Centralised Logging — The solution shall provide centralised collection and retention of relevant system, operational and security logs. | Must | IT Manager | TBD | BD-002 | CAP-005 |  | BRD v1.0 BR-010 | AD-09 | AD-07 | AD-11 | DD-007 — Logging & Audit Architecture |  | LLD-08 | LLD-01 | Not Yet Defined |  |  | Not Yet Defined | Required logs are centrally available for investigation and auditing and remain available following system events or restarts. | Baseline Pending Approval | TBD – delivery owner not assigned | BRD note: Persistent logging requirement strengthened following customer feedback. ¦ DF: No formal Discovery Finding IDs are defined in the BRD. CAP: No formal capability catalogue/IDs are defined in the BRD.
Not Yet Defined | BR-011 | Functional | Operational Monitoring and Alerting — The organisation requires proactive monitoring of infrastructure and service health, errors, backup status, security events and other operational risks. | Must | IT Manager | TBD | BD-002 | CAP-006 | CAP-005 | BRD v1.0 BR-011 | AD-09 | AD-10, AD-08, AD-07 | AD-02, AD-05, AD-06, AD-01, AD-04, AD-03, AD-12 | DD-006 — Monitoring & Alerting Architecture | DD-007 — Logging & Audit Architecture |  | LLD-01 | Not Yet Defined |  |  | Not Yet Defined | Defined critical operational events generate appropriate alerts or notifications. | Baseline Pending Approval | TBD – delivery owner not assigned | BRD note: Focused on routine operational monitoring. ¦ DF: No formal Discovery Finding IDs are defined in the BRD. CAP: No formal capability catalogue/IDs are defined in the BRD.
Not Yet Defined | BR-012 | Functional | Threat Detection — The solution shall provide mechanisms to identify potential security threats, suspicious activity and indicators of compromise. | Should | IT Manager | TBD | BD-002 | CAP-017 | CAP-005 CAP-006 | BRD v1.0 BR-012 | AD-08 | AD-09, AD-10, AD-03 | AD-02, AD-01, AD-05, AD-04 | DD-007 — Logging & Audit Architecture | DD-006 Monitoring & Alerting | Not Yet Defined |  | Not Yet Defined |  |  | Not Yet Defined | Relevant security events can be detected and investigated. | Baseline Pending Approval | TBD – delivery owner not assigned | BRD note: Implementation technology to be determined. ¦ DF: No formal Discovery Finding IDs are defined in the BRD. CAP: No formal capability catalogue/IDs are defined in the BRD.
Not Yet Defined | BR-013 | Functional | Business Continuity Backups — Business-critical systems and data shall be backed up automatically according to agreed business requirements. | Must | IT Manager | TBD | BD-002 | CAP-007 | CAP-002 | BRD v1.0 BR-013 | AD-07 | AD-12, AD-06, AD-10 | AD-09, AD-08, AD-02, AD-05, AD-01 | DD-005 — Backup & Recovery Architecture | DD-012 — Availability & Resilience Strategy |  | LLD-01 | Not Yet Defined |  |  | Not Yet Defined | Agreed backups complete successfully without requiring routine manual intervention. | Baseline Pending Approval | TBD – delivery owner not assigned | BRD note: Business continuity. ¦ DF: No formal Discovery Finding IDs are defined in the BRD. CAP: No formal capability catalogue/IDs are defined in the BRD.
Not Yet Defined | BR-014 | Functional | Backup Validation and Recovery Testing — The organisation requires routine validation of backup integrity through scheduled restoration and recovery testing. | Should | IT Manager | TBD | BD-002 | CAP-007 | CAP-002 | BRD v1.0 BR-014 | AD-07 | AD-10, AD-12, AD-02 | AD-06, AD-09, AD-08, AD-05 | DD-005 — Backup & Recovery Architecture | DD-012 — Availability & Resilience Strategy |  | LLD-01 | Not Yet Defined |  |  | Not Yet Defined | Successful restore and recovery tests are completed and documented at agreed intervals. | Baseline Pending Approval | TBD – delivery owner not assigned | BRD note: Supports disaster recovery objectives. ¦ DF: No formal Discovery Finding IDs are defined in the BRD. CAP: No formal capability catalogue/IDs are defined in the BRD.
Not Yet Defined | BR-015 | Functional | Service Recovery — The organisation requires documented and repeatable capabilities for recovering business-critical systems and services following service, configuration or system failure. | Must | IT Manager | TBD | BD-002 | CAP-007 | CAP-016 | BRD v1.0 BR-015 | AD-12 | AD-07, AD-10, AD-02 | AD-05, AD-06, AD-04, AD-03, AD-01, AD-09, AD-08 | DD-012 — Availability & Resilience Strategy | DD-005 — Backup & Recovery Architecture |  | LLD-01 | Not Yet Defined |  |  | Not Yet Defined | Agreed recovery procedures successfully restore affected services within defined recovery objectives. | Baseline Pending Approval | TBD – delivery owner not assigned | BRD note: Detailed RTO/RPO to be confirmed during design. ¦ DF: No formal Discovery Finding IDs are defined in the BRD. CAP: No formal capability catalogue/IDs are defined in the BRD.
Not Yet Defined | BR-016 | Functional | Application Resilience — Business-critical applications shall minimise single points of failure and support improved service resilience where justified by business requirements. | Must | Operations Director | TBD | BD-002 | CAP-010 |  | BRD v1.0 BR-016 | AD-12 | AD-05, AD-02, AD-01 | AD-06, AD-04, AD-09, AD-10, AD-08, AD-07 | DD-012 — Availability & Resilience Strategy | DD-001 — Compute / Platform Architecture DD-010 — Application Hosting Architecture | Not Yet Defined |  | Not Yet Defined |  |  | Not Yet Defined | Agreed critical services meet defined resilience requirements and expected failure scenarios are addressed. | Baseline Pending Approval | TBD – delivery owner not assigned | BRD note: High Availability remains a design decision. ¦ DF: No formal Discovery Finding IDs are defined in the BRD. CAP: No formal capability catalogue/IDs are defined in the BRD.
Not Yet Defined | BR-017 | Functional | Remote Administration — The IT team shall be able to securely administer infrastructure remotely. | Must | IT Manager | TBD | BD-001 | CAP-016 | CAP-008 CAP-017 | BRD v1.0 BR-017 | AD-10 | AD-08, AD-03, AD-01 | AD-02, AD-09, AD-04, AD-12 | DD-008 — Remote Administration Architecture | DD-002 — Identity & Access Management Architecture DD-009 — Network Security & Segmentation | LLD-01 |  | Not Yet Defined |  |  | Not Yet Defined | Authorised administrators can securely perform required administrative activities remotely. | Baseline Pending Approval | TBD – delivery owner not assigned | BRD note: Supports operational flexibility. ¦ DF: No formal Discovery Finding IDs are defined in the BRD. CAP: No formal capability catalogue/IDs are defined in the BRD.
Not Yet Defined | BR-018 | Functional | Secure Remote Access — Authorised users shall have secure remote access to business services where required. | Must | Operations Director | TBD | BD-002 | CAP-008 | CAP-017 CAP-001 | BRD v1.0 BR-018 | AD-01 | AD-08, AD-03, AD-05 | AD-09, AD-10, AD-11, AD-12, AD-04 | DD-008 — Remote Administration Architecture | DD-002 — Identity & Access Management Architecture DD-009 — Network Security & Segmentation | Not Yet Defined |  | Not Yet Defined |  |  | Not Yet Defined | Approved users can securely access authorised business resources remotely. | Baseline Pending Approval | TBD – delivery owner not assigned | BRD note: VPN and related technologies evaluated during design. ¦ DF: No formal Discovery Finding IDs are defined in the BRD. CAP: No formal capability catalogue/IDs are defined in the BRD.
Not Yet Defined | BR-019 | Functional | Network Security — The solution shall improve protection of the corporate network through appropriate security controls governing access to internal and external resources. | Must | IT Manager | TBD | BD-002 | CAP-017 | CAP-009 | BRD v1.0 BR-019 | AD-08 | AD-01, AD-03, AD-09 | AD-10, AD-05, AD-02, AD-11, AD-12 | DD-009 Network Security & Segmentation | DD-002 — Identity & Access Management Architecture | LLD-01 |  | Not Yet Defined |  |  | Not Yet Defined | Network access complies with approved security policies. | Baseline Pending Approval | TBD – delivery owner not assigned | BRD note: Technology to be determined. ¦ DF: No formal Discovery Finding IDs are defined in the BRD. CAP: No formal capability catalogue/IDs are defined in the BRD.
Not Yet Defined | BR-020 | Functional | Network Segmentation — The infrastructure shall support logical separation of business systems and services to improve security and operational resilience. | Should | IT Manager | TBD | BD-002 | CAP-009 | CAP-017 | BRD v1.0 BR-020 | AD-01 | AD-08, AD-12, AD-02 | AD-05, AD-10, AD-09, AD-03, AD-04 | DD-009 Network Security & Segmentation | DD-001 — Compute / Platform Architecture | LLD-01 |  | Not Yet Defined |  |  | Not Yet Defined | Business services are appropriately segregated according to agreed operational requirements. | Baseline Pending Approval | TBD – delivery owner not assigned | BRD note: Detailed design required. ¦ DF: No formal Discovery Finding IDs are defined in the BRD. CAP: No formal capability catalogue/IDs are defined in the BRD.
Not Yet Defined | BR-021 | Functional | Integration with Existing Business Services — The proposed solution shall integrate with existing business systems and cloud services where required to support business operations and migration activities. | Must | IT Manager | TBD | BD-001 | CAP-011 |  | BRD v1.0 BR-021 | AD-11 | AD-05, AD-03, AD-01 | AD-08, AD-10, AD-02, AD-09, AD-12 | DD-011 — Service Integration / Interoperability Architecture |  | Not Yet Defined |  | Not Yet Defined |  |  | Not Yet Defined | Existing business applications and required services continue to operate successfully following implementation. | Baseline Pending Approval | TBD – delivery owner not assigned | BRD note: Avoids committing to specific technologies. ¦ DF: No formal Discovery Finding IDs are defined in the BRD. CAP: No formal capability catalogue/IDs are defined in the BRD.
Not Yet Defined | BR-022 | Functional | Business Application Hosting — The infrastructure shall provide a reliable platform for hosting business-critical applications and supporting services. | Must | Operations Director | TBD | BD-003 | CAP-010 | CAP-015 | BRD v1.0 BR-022 | AD-02 | AD-12, AD-05, AD-06 | AD-01, AD-04, AD-08, AD-10, AD-09, AD-07 | DD-010 — Application Hosting Architecture | DD-001 — Compute / Platform Architecture DD-012 — Availability & Resilience Strategy | Not Yet Defined |  | Not Yet Defined |  |  | Not Yet Defined | Business applications operate reliably within agreed service levels. | Baseline Pending Approval | TBD – delivery owner not assigned | BRD note: Future expansion supported. ¦ DF: No formal Discovery Finding IDs are defined in the BRD. CAP: No formal capability catalogue/IDs are defined in the BRD.
Not Yet Defined | BR-023 | Functional | Infrastructure Scalability — The infrastructure shall support future organisational growth without significant redesign. | Should | IT Manager | TBD | BD-003 | - |  | BRD v1.0 BR-023 | AD-02 | AD-06, AD-01, AD-05 | AD-03, AD-04, AD-09, AD-10, AD-08, AD-07, AD-12 | DD-001 — Compute & Platform Architecture | DD-004 — Storage Architecture DD-009 — Network Security & Segmentation DD-012 — Availability & Resilience Strategy | LLD-01 |  | Not Yet Defined |  |  | Not Yet Defined | New users, departments and services can be introduced efficiently. | Baseline Pending Approval | TBD – delivery owner not assigned | BRD note: Five-year growth objective. ¦ DF: No formal Discovery Finding IDs are defined in the BRD. CAP: No formal capability catalogue/IDs are defined in the BRD.
Not Yet Defined | BR-024 | Functional | Infrastructure Standardisation — The organisation requires standardised infrastructure, configuration and operational practices to improve consistency and supportability. | Must | IT Manager | TBD | BD-001 | CAP-016 | CAP-002 | BRD v1.0 BR-024 | AD-10 | AD-02, AD-08, AD-04 | AD-01, AD-03, AD-05, AD-06, AD-09, AD-07, AD-12 | DD-001 — Compute / Platform Architecture | DD-011 — Automation & Scheduled Operations Architecture | LLD-01 |  | Not Yet Defined |  |  | Not Yet Defined | Agreed infrastructure and operational standards are documented and implemented. | Baseline Pending Approval | TBD – delivery owner not assigned | BRD note: Supports operational maturity. ¦ DF: No formal Discovery Finding IDs are defined in the BRD. CAP: No formal capability catalogue/IDs are defined in the BRD.
Not Yet Defined | BR-025 | Functional | Operational Documentation — The project shall provide and maintain appropriate technical and operational documentation, including SOPs, technical runbooks, recovery procedures and relevant user documentation. | Must | IT Manager | TBD | BD-001 | CAP-016 |  | BRD v1.0 BR-025 | AD-10 | AD-12, AD-07, AD-05 | AD-02, AD-01, AD-03, AD-04, AD-06, AD-08, AD-09, AD-11 | DD-011 — Automation & Scheduled Operations Architecture | DD-010 — Application Hosting Architecture DD-012 — Availability & Resilience Strategy | Not Yet Defined |  | Not Yet Defined |  |  | Not Yet Defined | Required documentation is complete, accurate and available at operational handover. | Baseline Pending Approval | TBD – delivery owner not assigned | BRD note: Distinguishes IT runbooks/SOPs from user documentation. ¦ DF: No formal Discovery Finding IDs are defined in the BRD. CAP: No formal capability catalogue/IDs are defined in the BRD.
Not Yet Defined | BR-026 | Functional | Reporting and Visibility — The solution shall provide appropriate operational, security, capacity and performance reporting to support IT operations and business decision making. | Should | Operations Director | TBD | BD-001 | CAP-012 | CAP-006 CAP-005 | BRD v1.0 BR-026 | AD-09 | AD-10, AD-08, AD-06 | AD-02, AD-05, AD-01, AD-07, AD-12, AD-03 | DD-006 — Monitoring & Alerting | DD-007 — Logging & Audit | Not Yet Defined |  | Not Yet Defined |  |  | Not Yet Defined | Required reports are available to authorised stakeholders at agreed intervals. | Baseline Pending Approval | TBD – delivery owner not assigned | BRD note: Reporting requirements to be confirmed during design. ¦ DF: No formal Discovery Finding IDs are defined in the BRD. CAP: No formal capability catalogue/IDs are defined in the BRD.
Not Yet Defined | BR-027 | Functional | Administrative Approval Workflows — The solution shall support business approval processes where required for administrative or operational activities. | Could | Operations Director | TBD | BD-001 | CAP-019 |  | BRD v1.0 BR-027 | AD-10 | AD-03, AD-08, AD-09 | AD-05, AD-02, AD-11 | No dedicated |  | Not Yet Defined |  | Not Yet Defined |  |  | Not Yet Defined | Agreed approval workflows are implemented for identified business processes. | Baseline Pending Approval | TBD – delivery owner not assigned | BRD note: Requires further requirements gathering. ¦ DF: No formal Discovery Finding IDs are defined in the BRD. CAP: No formal capability catalogue/IDs are defined in the BRD.
Not Yet Defined | BR-028 | Functional | Print Services — The proposed solution shall continue to support business printing services where required. | Should | Operations Manager | TBD | BD-001 | CAP-010 |  | BRD v1.0 BR-028 | AD-05 | AD-01, AD-03, AD-10 | AD-02, AD-08, AD-09, AD-12 | No dedicated | DD-009 — Network Security & Segmentation | Not Yet Defined |  | Not Yet Defined |  |  | Not Yet Defined | Business printing remains available following implementation. | Baseline Pending Approval | TBD – delivery owner not assigned | BRD note: Existing functionality retained. ¦ DF: No formal Discovery Finding IDs are defined in the BRD. CAP: No formal capability catalogue/IDs are defined in the BRD.
Not Yet Defined | BR-029 | Functional | IT Asset Management — Northwind shall maintain a formal and accurate process for recording, managing and reviewing IT assets, including ownership, lifecycle status and relevant operational information. | Must | IT Manager | TBD | BD-001 | CAP-018 |  | BRD v1.0 BR-029 | AD-10 | AD-02, AD-08, AD-09 | AD-01, AD-05, AD-11 | No dedicated | DD-001 — Compute / Platform Architecture | Not Yet Defined |  | Not Yet Defined |  |  | Not Yet Defined | An agreed asset inventory and ownership model is maintained and available to authorised stakeholders. | Baseline Pending Approval | TBD – delivery owner not assigned | BRD note: Introduced following Workshop 2. Initial asset baseline remains an outstanding dependency. ¦ DF: No formal Discovery Finding IDs are defined in the BRD. CAP: No formal capability catalogue/IDs are defined in the BRD.
Not Yet Defined | BR-030 | Functional | Software and System Update Management — The organisation shall have a controlled process for evaluating, testing, approving and deploying software and system updates. | Must | IT Manager | TBD | BD-001 | CAP-013 | CAP-019 | BRD v1.0 BR-030 | AD-10 | AD-08, AD-02, AD-12 | AD-05, AD-09, AD-07, AD-11 | DD-010 — Patch & Software Lifecycle Management Architecture | DD-011 — Automation & Scheduled Operations Architecture | Not Yet Defined |  | Not Yet Defined |  |  | Not Yet Defined | Agreed updates are evaluated and, where appropriate, validated in a controlled environment before production deployment. | Baseline Pending Approval | TBD – delivery owner not assigned | BRD note: Builds on Workshop 2 CR-006 and customer follow-up. ¦ DF: No formal Discovery Finding IDs are defined in the BRD. CAP: No formal capability catalogue/IDs are defined in the BRD.
Not Yet Defined | BR-031 | Functional | Software and Package Lifecycle Management — The solution shall support controlled installation, updating and removal of supported system software and packages. | Should | IT Manager | TBD | BD-001 | CAP-013 |  | BRD v1.0 BR-031 | AD-10 | AD-02, AD-08, AD-05 | AD-09, AD-12, AD-11 | DD-010 — Patch & Software Lifecycle Management Architecture |  | Not Yet Defined |  | Not Yet Defined |  |  | Not Yet Defined | Supported software can be installed, updated and removed through a documented and controlled process. | Baseline Pending Approval | TBD – delivery owner not assigned | BRD note: Business capability; implementation technology to be determined. ¦ DF: No formal Discovery Finding IDs are defined in the BRD. CAP: No formal capability catalogue/IDs are defined in the BRD.
Not Yet Defined | BR-032 | Functional | Administrative Automation — The organisation shall identify and implement appropriate opportunities to automate repetitive infrastructure administration activities where this provides operational benefit. | Should | IT Manager | TBD | BD-001 | CAP-002 | CAP-016 | BRD v1.0 BR-032 | AD-10 | AD-02, AD-03, AD-08 | AD-05, AD-06, AD-09, AD-07, AD-04, AD-01 | DD-011 — Automation & Scheduled Operations Architecture |  | Not Yet Defined |  | Not Yet Defined |  |  | Not Yet Defined | Agreed repetitive administrative activities are standardised or automated where practical. | Baseline Pending Approval | TBD – delivery owner not assigned | BRD note: Customer-requested capability; avoid prescribing automation technology. ¦ DF: No formal Discovery Finding IDs are defined in the BRD. CAP: No formal capability catalogue/IDs are defined in the BRD.
Not Yet Defined | BR-033 | Functional | Scheduled Administrative Activities — The solution shall support the controlled scheduling of routine administrative, maintenance and operational activities where appropriate. | Should | IT Manager | TBD | BD-001 | CAP-002 | CAP-016 | BRD v1.0 BR-033 | AD-10 | AD-02, AD-08, AD-09 | AD-07, AD-05, AD-06, AD-04, AD-12 | DD-011 — Automation & Scheduled Operations Architecture | DD-010 — Patch & Software Lifecycle Management Architecture | Not Yet Defined |  | Not Yet Defined |  |  | Not Yet Defined | Agreed recurring activities can be executed according to defined schedules and documented procedures. | Baseline Pending Approval | TBD – delivery owner not assigned | BRD note: Supports operational consistency. ¦ DF: No formal Discovery Finding IDs are defined in the BRD. CAP: No formal capability catalogue/IDs are defined in the BRD.
Not Yet Defined | BR-034 | Functional | Capacity and Performance Management — The organisation requires periodic assessment of infrastructure capacity, resource utilisation, performance and growth trends to support operational planning and future requirements. | Should | Operations Director | TBD | BD-003 | CAP-012 | CAP-006 | BRD v1.0 BR-034 | AD-10 | AD-09, AD-02, AD-06 | AD-01, AD-05, AD-07, AD-12, AD-04 | DD-006 — Monitoring & Alerting Architecture | DD-004 — Storage Architecture |  | LLD-01 | Not Yet Defined |  |  | Not Yet Defined | Capacity and performance information is collected and reviewed at agreed intervals, with identified issues recorded and addressed appropriately. | Baseline Pending Approval | TBD – delivery owner not assigned | BRD note: Separates management reporting from day-to-day monitoring. ¦ DF: No formal Discovery Finding IDs are defined in the BRD. CAP: No formal capability catalogue/IDs are defined in the BRD.
Not Yet Defined | BR-035 | Functional | System Time Consistency — The infrastructure shall maintain consistent and reliable system time across supported systems and services to support authentication, logging, auditing and troubleshooting. | Must | IT Manager | TBD | BD-002 | CAP-014 |  | BRD v1.0 BR-035 | AD-04 | AD-03, AD-09, AD-08 | AD-10, AD-02, AD-01, AD-05 | DD-007 — Logging & Audit Architecture |  |  | LLD-01 | Not Yet Defined |  |  | Not Yet Defined | Supported systems maintain time within agreed tolerance and deviations can be identified and addressed. | Baseline Pending Approval | TBD – delivery owner not assigned | BRD note: Customer-requested capability; technical implementation deferred to design. ¦ DF: No formal Discovery Finding IDs are defined in the BRD. CAP: No formal capability catalogue/IDs are defined in the BRD.
Not Yet Defined | BR-036 | Functional | Host Security Enforcement — Supported systems shall provide appropriate host-level security controls to restrict unauthorised access to system resources, services and data. | Must | IT Manager | TBD | BD-002 | CAP-017 | CAP-001 | BRD v1.0 BR-036 | AD-08 | AD-03, AD-02, AD-10 | AD-01, AD-05, AD-06, AD-09 | DD-009 — Network Security & Segmentation Architecture | DD-002 — Identity & Access Management Architecture DD-008 — Remote Administration Architecture | Not Yet Defined |  | Not Yet Defined |  |  | Not Yet Defined | Unauthorised access to protected system resources is prevented and agreed security controls are demonstrably enforced. | Baseline Pending Approval | TBD – delivery owner not assigned | BRD note: Business requirement deliberately technology-neutral. ¦ DF: No formal Discovery Finding IDs are defined in the BRD. CAP: No formal capability catalogue/IDs are defined in the BRD.
Not Yet Defined | BR-037 | Functional | Network Resource Access — The solution shall provide reliable and appropriately controlled access to authorised network-based resources with minimal unnecessary manual administration. | Should | IT Manager | TBD | BD-001 | CAP-009 | CAP-001 | BRD v1.0 BR-037 | AD-01 | AD-03, AD-08, AD-10 | AD-05, AD-04, AD-02, AD-09, AD-12 | DD-009 — Network Security & Segmentation Architecture | DD-002 — Identity & Access Management Architecture | LLD-01 |  | Not Yet Defined |  |  | Not Yet Defined | Authorised users and services can access required network resources according to defined access controls. | Baseline Pending Approval | TBD – delivery owner not assigned | BRD note: Detailed access and mounting mechanisms to be determined during design. ¦ DF: No formal Discovery Finding IDs are defined in the BRD. CAP: No formal capability catalogue/IDs are defined in the BRD.
Not Yet Defined | BR-038 | Functional | Incident Investigation and Troubleshooting — The IT team shall have documented processes and appropriate administrative capabilities to investigate, troubleshoot and resolve infrastructure and service issues. | Must | IT Manager | TBD | BD-002 | CAP-016 | CAP-005 CAP-006 | BRD v1.0 BR-038 | AD-10 | AD-09, AD-02, AD-08 | AD-01, AD-05, AD-03, AD-04, AD-06, AD-07, AD-12, AD-11 | DD-006 — Monitoring & Alerting Architecture | DD-007 — Logging & Audit DD-010 — Application Hosting Architecture | Not Yet Defined |  | Not Yet Defined |  |  | Not Yet Defined | Defined operational issues can be investigated using appropriate information, procedures and administrative capabilities, with recovery actions documented where required. | Baseline Pending Approval | TBD – delivery owner not assigned | BRD note: Supports operational recovery and knowledge transfer. ¦ DF: No formal Discovery Finding IDs are defined in the BRD. CAP: No formal capability catalogue/IDs are defined in the BRD.
Not Yet Defined | NFR-001 | Non-Functional | Availability — Business-critical services shall provide an appropriate level of availability aligned with agreed business requirements and service criticality. | Must | Operations Director | TBD | BD-002 | - |  | BRD v1.0 NFR-001 | AD-12 | AD-07 Backup & Recovery, AD-02 Compute & Platform, AD-09 Observability | AD-01, AD-04, AD-05, AD-06, AD-10 | DD-012 — Availability & Resilience Strategy | DD-005 — Backup & Recovery Architecture; DD-006 — Monitoring & Alerting Architecture | Not Yet Defined |  | Not Yet Defined |  |  | Not Yet Defined | Agreed critical services meet defined availability targets. | Baseline Pending Approval | TBD – delivery owner not assigned | BRD note: HA remains a design decision. ¦ DF: No formal Discovery Finding IDs are defined in the BRD. CAP: No formal capability catalogue/IDs are defined in the BRD.
Not Yet Defined | NFR-002 | Non-Functional | Reliability — The solution shall operate reliably under normal expected operating conditions and minimise avoidable service interruptions. | Must | Operations Director | TBD | BD-002 | - |  | BRD v1.0 NFR-002 | AD-12 | AD-02 Compute & Platform, AD-10 Management & Operations, AD-09 Observability | AD-01, AD-04, AD-05, AD-06, AD-07, AD-08 | DD-012 — Availability & Resilience Strategy | DD-006 — Monitoring & Alerting Architecture | LLD-01 |  | Not Yet Defined |  |  | Not Yet Defined | Services operate consistently during agreed operational testing. | Baseline Pending Approval | TBD – delivery owner not assigned | BRD note: Supports resilience. ¦ DF: No formal Discovery Finding IDs are defined in the BRD. CAP: No formal capability catalogue/IDs are defined in the BRD.
Not Yet Defined | NFR-003 | Non-Functional | Performance — Infrastructure and services shall provide sufficient performance to support current business operations and anticipated growth. | Must | Operations Director | TBD | BD-003 | - | CAP-006 | BRD v1.0 NFR-003 | AD-02 | AD-06 Storage, AD-09 Observability, AD-01 Network | AD-05, AD-10, AD-12 | DD-006 — Monitoring & Alerting Architecture | DD-001 — Compute / Virtualisation; DD-004 — Storage Architecture | LLD-01 |  | Not Yet Defined |  |  | Not Yet Defined | Agreed performance criteria are met under representative workloads. | Baseline Pending Approval | TBD – delivery owner not assigned | BRD note: Links to capacity management. ¦ DF: No formal Discovery Finding IDs are defined in the BRD. CAP: No formal capability catalogue/IDs are defined in the BRD.
Not Yet Defined | NFR-004 | Non-Functional | Scalability — The solution shall support anticipated growth in users, data, services and infrastructure without requiring disproportionate redesign or administrative effort. | Should | IT Manager | TBD | BD-003 | - |  | BRD v1.0 NFR-004 | AD-02 | AD-06 Storage, AD-01 Network, AD-10 Management & Operations | AD-03, AD-04, AD-05, AD-09, AD-12 | DD-001 — Compute / Virtualisation | DD-004 — Storage Architecture; DD-012 — Availability & Resilience Strategy | Not Yet Defined |  | Not Yet Defined |  |  | Not Yet Defined | Additional users, services and capacity can be introduced using defined processes. | Baseline Pending Approval | TBD – delivery owner not assigned | BRD note: Five-year growth considerations. ¦ DF: No formal Discovery Finding IDs are defined in the BRD. CAP: No formal capability catalogue/IDs are defined in the BRD.
Not Yet Defined | NFR-005 | Non-Functional | Security — The solution shall implement appropriate security controls to protect systems, services and business information from unauthorised access, misuse and compromise. | Must | IT Manager | TBD | BD-002 | CAP-017 |  | BRD v1.0 NFR-005 | AD-08 | AD-03 Identity & Access, AD-01 Network, AD-10 Management & Operations | AD-02, AD-05, AD-06, AD-09, AD-11 | DD-009 — Network Security & Segmentation Architecture | DD-002 — Identity & Access Management Architecture; DD-008 — Remote & Administrative Access Architecture | Not Yet Defined |  | Not Yet Defined |  |  | Not Yet Defined | Agreed security controls are implemented and validated. | Baseline Pending Approval | TBD – delivery owner not assigned | BRD note: Technology-neutral. ¦ DF: No formal Discovery Finding IDs are defined in the BRD. CAP: No formal capability catalogue/IDs are defined in the BRD.
Not Yet Defined | NFR-006 | Non-Functional | Auditability — Relevant administrative, operational and security activities shall be sufficiently recorded to support investigation, troubleshooting and accountability. | Must | IT Manager | TBD | BD-002 | CAP-005 |  | BRD v1.0 NFR-006 | AD-09 | AD-08 Security, AD-10 Management & Operations, AD-03 Identity & Access | AD-02, AD-05, AD-11 | DD-007 — Logging & Audit Architecture | DD-002 — Identity & Access Management Architecture | Not Yet Defined |  | Not Yet Defined |  |  | Not Yet Defined | Required events can be reviewed using retained records and logs. | Baseline Pending Approval | TBD – delivery owner not assigned | BRD note: Complements BR-010. ¦ DF: No formal Discovery Finding IDs are defined in the BRD. CAP: No formal capability catalogue/IDs are defined in the BRD.
Not Yet Defined | NFR-007 | Non-Functional | Data Protection — Business information shall be protected against unauthorised access, accidental loss, corruption and inappropriate modification. | Must | Finance Manager | TBD | BD-002 | CAP-017 | CAP-007 CAP-001 | BRD v1.0 NFR-007 | AD-08 | AD-03 Identity & Access, AD-07 Backup & Recovery, AD-06 Storage | AD-05, AD-09, AD-10, AD-11 | DD-009 — Network Security & Segmentation Architecture | DD-002 — Identity & Access Management Architecture; DD-005 — Backup & Recovery Architecture | Not Yet Defined |  | Not Yet Defined |  |  | Not Yet Defined | Appropriate access, protection and recovery controls are demonstrated. | Baseline Pending Approval | TBD – delivery owner not assigned | BRD note: Complements BR-008/009. ¦ DF: No formal Discovery Finding IDs are defined in the BRD. CAP: No formal capability catalogue/IDs are defined in the BRD.
Not Yet Defined | NFR-008 | Non-Functional | Maintainability — Infrastructure and services shall be designed and implemented so that routine administration, maintenance, updates and troubleshooting can be performed efficiently and consistently. | Must | IT Manager | TBD | BD-001 | CAP-016 | CAP-002 CAP-013 | BRD v1.0 NFR-008 | AD-10 | AD-02 Compute & Platform, AD-24-equivalent standardisation via BR-024 / AD-08 Security, AD-09 Observability | AD-01, AD-04, AD-05, AD-06, AD-07 | DD-011 — Automation & Scheduled Operations Architecture | DD-010 — Patch & Software Lifecycle Management Architecture; DD-001 — Compute / Virtualisation | Not Yet Defined |  | Not Yet Defined |  |  | Not Yet Defined | Routine maintenance activities can be performed using documented procedures without unnecessary complexity. | Baseline Pending Approval | TBD – delivery owner not assigned | BRD note: Strengthened following Workshop 2. ¦ DF: No formal Discovery Finding IDs are defined in the BRD. CAP: No formal capability catalogue/IDs are defined in the BRD.
Not Yet Defined | NFR-009 | Non-Functional | Recoverability — Business-critical services shall be capable of recovery within agreed service-specific recovery objectives following an incident or failure. | Must | IT Manager | TBD | BD-002 | CAP-007 |  | BRD v1.0 NFR-009 | AD-07 | AD-12 Resilience & Availability, AD-10 Management & Operations, AD-02 Compute & Platform | AD-05, AD-06, AD-09, AD-04, AD-03 | DD-012 — Availability & Resilience Strategy | DD-005 — Backup & Recovery Architecture | Not Yet Defined |  | Not Yet Defined |  |  | Not Yet Defined | Recovery testing demonstrates that agreed RTO/RPO objectives can be achieved. | Baseline Pending Approval | TBD – delivery owner not assigned | BRD note: Northwind's current expectation is 4 hours; service-specific objectives to be confirmed during design. ¦ DF: No formal Discovery Finding IDs are defined in the BRD. CAP: No formal capability catalogue/IDs are defined in the BRD.
Not Yet Defined | NFR-010 | Non-Functional | Supportability — The solution shall be supported by appropriate documentation, operational procedures, troubleshooting information and knowledge transfer. | Must | IT Manager | TBD | BD-001 | CAP-016 |  | BRD v1.0 NFR-010 | AD-10 | AD-09 Observability, AD-02 Compute & Platform, AD-12 Resilience & Availability | AD-05, AD-07, AD-08, AD-03, AD-04 | DD-011 — Automation & Scheduled Operations Architecture | DD-010 — Patch & Software Lifecycle Management Architecture; DD-012 — Availability & Resilience Strategy | Not Yet Defined |  | Not Yet Defined |  |  | Not Yet Defined | Required SOPs, runbooks, recovery procedures and knowledge transfer are completed before operational handover. | Baseline Pending Approval | TBD – delivery owner not assigned | BRD note: Stronger link to Workshop 2 CR-004. ¦ DF: No formal Discovery Finding IDs are defined in the BRD. CAP: No formal capability catalogue/IDs are defined in the BRD.
Not Yet Defined | NFR-011 | Non-Functional | Administrative Simplicity — The solution should minimise unnecessary manual administration and support standardised and repeatable operational processes. | Should | IT Manager | TBD | BD-001 | CAP-016 | CAP-002 | BRD v1.0 NFR-011 | AD-10 | AD-02 Compute & Platform, AD-03 Identity & Access, AD-08 Security | AD-04, AD-05, AD-09, AD-01 | DD-011 — Automation & Scheduled Operations Architecture | DD-001 — Compute / Virtualisation | Not Yet Defined |  | Not Yet Defined |  |  | Not Yet Defined | Identified repetitive activities are standardised or automated where practical. | Baseline Pending Approval | TBD – delivery owner not assigned | BRD note: Supports BR-032/033. ¦ DF: No formal Discovery Finding IDs are defined in the BRD. CAP: No formal capability catalogue/IDs are defined in the BRD.
Not Yet Defined | NFR-012 | Non-Functional | Compatibility — The solution shall remain compatible with required existing business applications, services, user workflows and supporting infrastructure. | Must | IT Manager | TBD | BD-001 | CAP-011 | - | BRD v1.0 NFR-012 | AD-11 | AD-05 Application & Business Services, AD-03 Identity & Access, AD-01 Network | AD-02, AD-08, AD-10, AD-04 | DD-003 — File & Data Services Architecture | DD-001 — Compute / Virtualisation; DD-008 — Remote & Administrative Access Architecture | Not Yet Defined |  | Not Yet Defined |  |  | Not Yet Defined | Existing agreed business services continue to operate following implementation. | Baseline Pending Approval | TBD – delivery owner not assigned | BRD note: Migration consideration. ¦ DF: No formal Discovery Finding IDs are defined in the BRD. CAP: No formal capability catalogue/IDs are defined in the BRD.
Not Yet Defined | NFR-013 | Non-Functional | Compliance — The solution shall support Northwind's applicable legal, regulatory, contractual and internal policy obligations. | Must | Operations Director | TBD | BD-002 | - |  | BRD v1.0 NFR-013 | AD-08 | AD-10 Management & Operations, AD-09 Observability, AD-03 Identity & Access | AD-05, AD-06, AD-07, AD-11 | DD-009 — Network Security & Segmentation Architecture | DD-007 — Logging & Audit Architecture; DD-010 — Patch & Software Lifecycle Management Architecture | Not Yet Defined |  | Not Yet Defined |  |  | Not Yet Defined | Relevant obligations are identified and addressed in the design. | Baseline Pending Approval | TBD – delivery owner not assigned | BRD note: No specific regulation assumed. ¦ DF: No formal Discovery Finding IDs are defined in the BRD. CAP: No formal capability catalogue/IDs are defined in the BRD.
Not Yet Defined | NFR-014 | Non-Functional | Monitoring and Observability — The solution shall provide sufficient visibility into service health, system behaviour, capacity, performance and relevant security events to support effective operational management. | Must | IT Manager | TBD | BD-002 | CAP-006 | CAP-005 CAP-012 | BRD v1.0 NFR-014 | AD-09 | AD-10 Management & Operations, AD-08 Security, AD-02 Compute & Platform | AD-01, AD-04, AD-05, AD-06, AD-07, AD-12 | DD-006 — Monitoring & Alerting Architecture | DD-007 — Logging & Audit Architecture | Not Yet Defined |  | Not Yet Defined |  |  | Not Yet Defined | IT personnel can obtain the information required to identify and investigate agreed operational conditions. | Baseline Pending Approval | TBD – delivery owner not assigned | BRD note: Strengthened to reflect Workshop 2 distinction between monitoring and capacity management. ¦ DF: No formal Discovery Finding IDs are defined in the BRD. CAP: No formal capability catalogue/IDs are defined in the BRD.
Not Yet Defined | NFR-015 | Non-Functional | Extensibility — The solution shall provide a foundation that can accommodate future services, capabilities and Statements of Work without requiring fundamental redesign. | Should | IT Manager | TBD | BD-003 | - |  | BRD v1.0 NFR-015 | AD-02 | AD-01 Network, AD-10 Management & Operations, AD-11 Integration | AD-03, AD-04, AD-05, AD-06, AD-08, AD-09, AD-12 | DD-001 — Compute / Virtualisation | DD-004 — Storage Architecture; DD-012 — Availability & Resilience Strategy | Not Yet Defined |  | Not Yet Defined |  |  | Not Yet Defined | Future agreed capabilities can be introduced using the established architecture and operational model. | Baseline Pending Approval | TBD – delivery owner not assigned | BRD note: Supports long-term roadmap. ¦ DF: No formal Discovery Finding IDs are defined in the BRD. CAP: No formal capability catalogue/IDs are defined in the BRD.
Not Yet Defined | NFR-016 | Non-Functional | Operational Consistency — Infrastructure configuration and operational activities shall follow documented and repeatable standards to reduce variation and human error. | Must | IT Manager | TBD | BD-001 | CAP-016 | CAP-002 | BRD v1.0 NFR-016 | AD-10 | AD-02 Compute & Platform, AD-08 Security, AD-09 Observability | AD-01, AD-03, AD-04, AD-05, AD-06, AD-07 | DD-011 — Automation & Scheduled Operations Architecture | DD-001 — Compute / Virtualisation; DD-010 — Patch & Software Lifecycle Management Architecture | Not Yet Defined |  | Not Yet Defined |  |  | Not Yet Defined | Agreed standards are documented and consistently applied across supported systems. | Baseline Pending Approval | TBD – delivery owner not assigned | BRD note: New v1.0 NFR. ¦ DF: No formal Discovery Finding IDs are defined in the BRD. CAP: No formal capability catalogue/IDs are defined in the BRD.
Not Yet Defined | NFR-017 | Non-Functional | Recoverable Operations — The solution shall support safe restoration of services following operational errors, configuration changes, software failures or infrastructure incidents. | Must | IT Manager | TBD | BD-002 | CAP-007 | CAP-016 | BRD v1.0 NFR-017 | AD-12 | AD-07 Backup & Recovery, AD-10 Management & Operations, AD-02 Compute & Platform | AD-05, AD-06, AD-09, AD-08 | DD-012 — Availability & Resilience Strategy | DD-005 — Backup & Recovery Architecture; DD-010 — Patch & Software Lifecycle Management Architecture | Not Yet Defined |  | Not Yet Defined |  |  | Not Yet Defined | Defined recovery procedures can restore affected services to an agreed operational state. | Baseline Pending Approval | TBD – delivery owner not assigned | BRD note: Distinguishes operational recovery from backup itself. ¦ DF: No formal Discovery Finding IDs are defined in the BRD. CAP: No formal capability catalogue/IDs are defined in the BRD.
Not Yet Defined | NFR-018 | Non-Functional | Time Consistency — Supported infrastructure shall maintain sufficiently consistent system time to support authentication, logging, auditing, monitoring and troubleshooting. | Must | IT Manager | TBD | BD-002 | CAP-014 |  | BRD v1.0 NFR-018 | AD-04 | AD-03 Identity & Access, AD-09 Observability, AD-08 Security | AD-10, AD-02, AD-01, AD-05 | DD-007 — Logging & Audit Architecture |  | Not Yet Defined |  | Not Yet Defined |  |  | Not Yet Defined | Systems maintain time within an agreed tolerance and time deviations can be detected. | Baseline Pending Approval | TBD – delivery owner not assigned | BRD note: Added following Sarah's email. ¦ DF: No formal Discovery Finding IDs are defined in the BRD. CAP: No formal capability catalogue/IDs are defined in the BRD.

## Legend & Reference
RTM Legend & Reference
Definitions and baseline rules for maintaining the Northwind Outdoor Ltd. RTM.
Code / Field | Meaning | How it is used in this RTM | Baseline value / rule
DF | Discovery Finding | Links a requirement to a formal discovery finding. | TBD — BRD v1.0 does not define individual Discovery Finding IDs.
BD | Business Driver | Business reason supporting the requirement. | Preserved exactly from BRD v1.0: BD-001, BD-002 or BD-003.
CAP | Capability | Business or technical capability supported by the requirement. | TBD — BRD v1.0 does not define a formal capability catalogue or IDs.
BRD | Business Requirements Document | Approved baseline requirement source. | BRD v1.0, Section 8 (functional) or Section 9 (non-functional).
SOW | Statement of Work | Delivery scope, activities, tests and deliverables. | Not Yet Defined — allocated after requirements prioritisation and delivery planning.
Sprint | Sprint | Delivery iteration in which work is scheduled. | Not Yet Defined — project sprint plan has not been approved.
HLD | High-Level Design | Architecture and solution-direction reference. | Not Yet Defined — HLD follows BRD approval.
LLD | Low-Level Design | Detailed technical implementation reference. | Not Yet Defined — created after HLD and SoW definition.
ADR | Architecture Decision Record | Record of a significant architectural decision. | Not Yet Defined — created only when a decision is made.
Test / UAT | Test or User Acceptance Test reference | Evidence that the requirement has been verified. | Not Yet Defined — developed during testing planning.
Status | Lifecycle status | Current requirement position in the delivery lifecycle. | Baseline Pending Approval — BRD v1.0 states its status is Pending Approval.
Owner | Delivery owner | Person/team accountable for progressing delivery. | TBD — delivery ownership is not assigned in BRD v1.0.
Priority | MoSCoW priority | Relative delivery priority. | Preserved exactly from the BRD requirement tables.
Business Owner | Requirement owner | Northwind stakeholder accountable for the business requirement. | Preserved exactly from the BRD requirement tables.
Maintenance note: Update delivery and verification references only when the relevant SoW, design, decision, test or acceptance evidence has been formally created. Do not replace TBD values with assumptions.

## Architecture Domains
# | Architecture Domain | What we'll design at HLD level | Example capabilities inside it
AD-01 | Network Architecture | How systems/users connect and how networks are logically separated | VLANs, routing, firewall boundaries, Internet access, remote connectivity
AD-02 | Compute & Platform Architecture | Where workloads run | Proxmox/virtualisation, Linux VMs, server roles, sandbox/production separation
AD-03 | Identity & Access Architecture | How people/systems authenticate and receive access | Users, groups, authentication, sudo/admin access, joiners/leavers
AD-04 | Core Infrastructure Services | Fundamental services other systems depend upon | DNS, DHCP, NTP/time synchronisation
AD-05 | Application & Business Services | Services directly consumed by Northwind users/business processes | File sharing, printing, internal applications/web services
AD-06 | Storage Architecture | How persistent data is stored and expanded | Filesystems, logical storage, capacity, growth
AD-07 | Backup & Recovery Architecture | How data/services are protected and recovered | Backups, retention, restore testing, RPO/RTO
AD-08 | Security Architecture | Security principles and trust boundaries across the environment | Segmentation, least privilege, firewalling, SELinux, hardening
AD-09 | Observability Architecture | How we know what the environment is doing | Monitoring, logging, alerting, capacity metrics
AD-10 | Management & Operations Architecture | How IT operates and maintains the environment | SSH/admin access, patching, software management, maintenance, operational procedures
AD-11 | Integration Architecture | How Northwind systems interact with external/existing platforms | Microsoft 365, external services, future integrations
AD-12 | Resilience & Availability Architecture | How the architecture responds to failures | Redundancy, failure domains, HA decisions, service dependencies

## Capabilities
Capability ID | Capability | Business Purpose | Architecture Domain
CAP-001 | Identity & Access Management | Provides centralised management of user identities, roles and access throughout the user lifecycle. | Identity & Access Architecture
CAP-002 | Automation & Scheduled Operations | Reduces repetitive manual administration and improves consistency by enabling repeatable and scheduled operational tasks. | Management & Operations Architecture
CAP-003 | File & Data Services | Enables authorised users to store, organise, locate and share business files using a consistent structure. | Application & Business Services
CAP-004 | Storage Provisioning/Management | Provides appropriately sized, accessible and manageable persistent storage to support business data, applications and infrastructure services. | Storage Architecture
CAP-005 | Logging & Audit | Clear audit trail of system changes and activity captured from a range of devices and services. | Observability Architecture
CAP-006 | Monitoring & Alerting | Provides visibility of service availability, health, resource utilisation and abnormal conditions, with timely alerting to enable proactive operational response. | Observability Architecture
CAP-007 | Backup & Recovery | In cases of outages, errors etc. business needs recent backups and proven process to restore from backups efficiently. | Backup & Recovery Architecture
CAP-008 | Remote Access | Authorised users can perform their jobs from outside the office environment | Network Architecture
CAP-009 | Network Connectivity & Core Network Services | Business needs system to system and user to system communications, service discovery and name resolutions, network config, prevent unauthorised access | Network Architecture
CAP-010 | Application Hosting | Northwind requires infrastructure capable of running and supporting business applications. | Application & Business Services
CAP-011 | Service Integration / Interoperability | New infrastructure should be capable of interoperating with existing business services | Integration Architecture
CAP-012 | Reporting | Business wants to generate statistics/KPIs regarding the current systems and services to influence decisions re growth, investment, changes etc. | Management & Operations Architecture
CAP-013 | Software & Patch Management | Admins must be able to control the software lifecycle, run and test updates, revert if errors encountered | Management & Operations Architecture
CAP-014 | Time Synchronisation Services | Maintains a consistent time reference across infrastructure and services to support reliable authentication, scheduling, monitoring, logging and investigation. | Core Infrastructure Services
CAP-015 | Compute Provisioning / Compute Hosting | Provides the processing resources and execution environments required to run Northwind infrastructure and business workloads. | Compute & Platform Architecture
CAP-016 | Systems Administration & Management | Provides authorised administrators with secure mechanisms to configure, operate, maintain and troubleshoot infrastructure services. | Management & Operations Architecture
CAP-017 | Security | Business needs designated security tools to protect systems, services and business information from unauthorised access, misuse and compromise. | Security Architecture
CAP-018 | Asset & Configuration Management | Provides an authoritative record of infrastructure and technology assets, their ownership, status and lifecycle to support effective administration and planning. | Management & Operations Architecture
CAP-019 | [CONDITIONAL] Governance / Approval Workflow Support | Some requests may need business approval not only technical access / ability | Management & Operations Architecture